## Export Worksheet
姓名 | 开发任务名称 | 需求名称 | 分配任务的预计工作量 | 任务的预计工作量 | 任务的预计开始时间 | 任务的预计结束时间 | 任务的实际开始时间 | 任务的实际结束时间 | 开发任务的实际工时 | 需求BUG数 | 需求修改BUG耗时 | 需求对应BUG的平均工时
陈诫孚 | 建信基金系统用户拆分（框架调整） | 建信基金系统用户拆分（框架调整） |  | 10 | 2018-04-05 | 2018-04-27 | 2018-04-12 | 2018-04-23 | 4 | 1 | 0.5625 | 0.12329
陈诫孚 | 用户管理-修改密码 | 用户管理-修改密码 |  | 1 | 2018-04-12 | 2018-04-13 | 2018-04-16 | 2018-04-16 | 0.5 | 2 | 0.5 | 0.5
陈诫孚 | 登录传输过程中密码加密 | 登录传输过程中密码加密 |  | 1 | 2018-05-11 | 2018-05-11 | 2018-05-11 | 2018-05-11 | 0.375
陈诫孚 | 流程图中备注字段加长 | 流程图中备注字段加长 |  | 0.5 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 0.5 | 1 | 0.125 | 0.2
陈诫孚 | 银河基金sirm域用户同步需求修改 | 银河基金sirm域用户同步需求修改 |  | 1.5 | 2018-05-23 | 2018-05-24 | 2018-05-23 | 2018-05-23 | 0.375
陈诫孚 | 云估值-增加redis处理 | 云估值-增加redis处理 |  | 4 | 2018-06-06 | 2018-06-08 | 2018-06-05 | 2018-06-08 | 2.25
陈诫孚 | 民生证券安全漏洞修复 | 民生证券安全漏洞修复 | 4 | 4 | 2018-06-27 | 2018-06-29 | 2018-06-26 | 2018-06-27 | 1.1875 | 1 | 0.1875 | 0.13636
陈雷 | 银河基金sirm券商路演需求 | 银河基金sirm券商路演需求 | 3 | 3 | 2018-03-27 | 2018-04-06 | 2018-04-02 | 2018-04-03 | 1.75 | 3 | 0.1875 | 0.096774
陈雷 | 晨会数据迁移及功能迁移 | 晨会数据迁移及功能迁移 | 5 | 5 | 2018-04-04 | 2018-04-13 | 2018-04-04 | 2018-04-17 | 7.3125 | 6 | 0.21875 | 0.029046
陈雷 | 晨会录入需要支持附件上传 | 晨会录入需要支持附件上传 | 1 | 1 | 2018-04-11 | 2018-04-12 | 2018-04-18 | 2018-04-18 | 0.625 | 1 | 0.03125 | 0.047619
陈雷 | 交银外出调研申请新增链接报告 | 交银外出调研申请新增链接报告 | 4 | 4 | 2018-04-16 | 2018-04-20 | 2018-04-19 | 2018-04-20 | 1.9688 | 5 | 0.5 | 0.20253
陈雷 | 华泰柏瑞路演打分需求变更-20180417 | 华泰柏瑞路演打分需求变更 | 2 | 3 | 2018-04-23 | 2018-04-30 | 2018-05-02 | 2018-04-26 | 0 | 13 | 1.775 | 1
陈雷 | 银河基金sirm券商路演优化需求 | 银河基金sirm券商路演优化需求 | 2 | 2 | 2018-04-24 | 2018-04-27 | 2018-04-25 | 2018-04-25 | 1 | 6 | 0.4375 | 0.30435
陈雷 | 长盛基金会议管理需求 | 长盛基金会议管理需求 | 4 | 4 | 2018-05-03 | 2018-05-10 | 2018-05-02 | 2018-05-04 | 2.3125 | 4 | 0.5 | 0.17778
陈雷 | API升级支持附件 | API升级支持附件 | 3 | 3 | 2018-05-03 | 2018-05-09 | 2018-05-07 | 2018-05-22 | 3.25
陈雷 | 客户服务录入统计 | 客户服务录入统计 | 5 | 5 | 2018-05-14 | 2018-05-18 | 2018-05-09 | 2018-05-21 | 5.9375 | 13 | 0.875 | 0.12844
陈雷 | 外出调研对接OA | 外出调研对接OA | 4 | 4 | 2018-05-29 | 2018-06-07 | 2018-05-28 | 2018-05-30 | 2.375 | 3 | 0.5625 | 0.19149
陈雷 | 外出管理 | 外出管理 | 3 | 3 | 2018-05-30 | 2018-06-01 | 2018-05-31 | 2018-05-30 | 0.25 | 2 | 0.125 | 0.33333
陈雷 | 长盛会议需求变更 | 长盛会议需求变更 | 2 | 2 | 2018-05-31 | 2018-06-01 | 2018-05-24 | 2018-05-24 | 0.5
陈雷 | 定制化调研开发 | 定制化调研开发 | 9 | 9 | 2018-06-01 | 2018-07-05 | 2018-06-01 | 2018-06-04 | 1.875 | 1 | 0.125 | 0.0625
陈雷 | 银河基金sirm券商路演邮件发送提醒修改 | 银河基金sirm券商路演邮件发送提醒修改 | 2 | 2 | 2018-06-01 | 2018-06-06 | 2018-05-31 | 2018-05-31 | 1
陈雷 | 报告提交流程名称，如果修改报告名称，流程内容同时修改 | 报告提交流程名称，如果修改报告名称，流程内容同时修改 | 1 | 1 | 2018-06-04 | 2018-06-06 | 2018-06-05 | 2018-06-05 | 0.625
陈雷 | 0605招商投研晨会以及工作计划修改 | 0605招商投研晨会以及工作计划修改 | 2 | 2 | 2018-06-06 | 2018-06-07 | 2018-06-05 | 2018-06-08 | 2.75 | 1 | 0.25 | 0.083333
陈雷 | 交银外出调研申请新增链接报告-20180608 | 交银外出调研申请新增链接报告 | 1 | 1 | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08 | 0.5 | 5 | 0.5 | 0.5
陈雷 | 晨会评论去掉全部终止掉 | 晨会评论去掉全部终止掉 | 1 | 1 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-13 | 1
董杰 | 持续管理(转移) | 持续管理(转移) | 3 | 7 | 2018-05-28 | 2018-06-05 | 2018-05-28 | 2018-06-08 | 7 | 16 | 0.85 | 0.10828
董杰 | 黑白名单查询(转移) | 黑白名单查询(转移) | 5 | 5 | 2018-05-28 | 2018-06-01 | 2018-05-28 | 2018-06-04 | 3 | 5 | 0.0375 | 0.012346
段思敏 | 模型配置 | 模型配置 | 8 | 11 | 2018-04-27 | 2018-05-11 | 2018-04-26 | 2018-05-11 | 6 | 28 | 2.975 | 0.33148
段思敏 | 主体信息维护，财务数据 | 主体信息维护，财务数据 | 8 | 5 | 2018-04-30 | 2018-05-08 | 2018-04-26 | 2018-05-09 | 6 | 6 | 0.9625 | 0.13824
段思敏 | 债项评级 | 债项评级 | 5 | 5 | 2018-05-10 | 2018-05-16 | 2018-05-09 | 2018-05-21 | 7 | 14 | 1.8 | 0.20455
段思敏 | 每日新债 | 每日新债 | 5 | 5 | 2018-05-21 | 2018-05-31 | 2018-05-21 | 2018-06-01 | 4.0125 | 26 | 2.85 | 0.4153
段思敏 | 债券评级查询、变动、全景图 | 债券评级查询、变动、全景图 | 6 | 6 | 2018-05-25 | 2018-06-01 | 2018-05-25 | 2018-06-01 | 3.6875 | 23 | 2.1625 | 0.36966
段思敏 | 债项规则变更 | 债项规则变更 | 2 | 2 | 2018-06-20 | 2018-06-21 | 2018-06-20 | 2018-06-20 | 0.625 | 4 | 0.3 | 0.32432
高书敏 | 事件驱动2(转移) | 事件驱动(转移) | 10 | 10 | 2018-04-08 | 2018-04-22 | 2018-03-06 | 2018-04-20 | 9.8125 | 14 | 4.8 | 0.32849
高书敏 | 事件驱动-联调测试 | 事件驱动-联调测试 | 10 | 20 | 2018-04-09 | 2018-04-15 | 2018-04-02 | 2018-04-20 | 2.8 | 11 | 5.075 | 0.64444
郭晶 | 报告模版需求分析 | 报告模版需求分析 | 8 | 9 | 2018-04-03 | 2018-04-13 | 2018-04-03 | 2018-04-13 | 7.625 | 11 | 3.375 | 0.30682
郭晶 | 银行组报告模板中EPS公式调整（股东净利润） | 银行组报告模板中EPS公式调整（股东净利润） | 1 | 1 | 2018-04-11 | 2018-04-13 | 2018-04-12 | 2018-04-12 | 0.25
郭晶 | A股估值模型-资产负债表字段补充 | A股估值模型-资产负债表字段补充 | 1 | 1 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 0.5
郭晶 | 信评内部报告修改需求 | 信评内部报告修改需求 | 2 | 2 | 2018-04-16 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 1.9375 | 11 | 0.4625 | 0.19271
郭晶 | 报告模板需求开发-尾页更新2 | 报告模板需求开发 | 9 | 9 | 2018-04-18 | 2018-06-01 | 2018-05-28 | 2018-05-29 | 8.3125 | 49 | 10.8875 | 0.56706
郭晶 | A股估值模型-券商财务模型 | A股估值模型-券商财务模型 | 7 | 7 | 2018-04-26 | 2018-05-04 | 2018-03-27 | 2018-05-04 | 6.875 | 1 | 0.125 | 0.017857
郭晶 | excel插件更新 | excel插件更新 | 1 | 1 | 2018-05-03 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 1 | 4 | 0.25 | 0.2
郭晶 | 晨会修改 | 晨会修改 | 1 | 1 | 2018-05-08 | 2018-05-09 | 2018-05-08 | 2018-05-09 | 0.875 | 2 | 0.25 | 0.22222
郭晶 | 长盛行业配置需求 | 长盛行业配置需求 | 2 | 8 | 2018-05-09 | 2018-05-18 | 2018-05-11 | 2018-05-16 | 2.875 | 7 | 1.3125 | 0.31343
郭晶 | 广发-报告模版开发 | 广发-报告模版开发 | 2 | 7 | 2018-05-14 | 2018-05-22 | 2018-05-14 | 2018-05-22 | 0.9375 | 20 | 2.2 | 0.7012
郭晶 | 晨会修改1 | 晨会修改 | 1 | 1 | 2018-05-22 | 2018-05-22 | 2018-05-23 | 2018-05-22 | 0.125 | 2 | 0.25 | 0.66667
郭晶 | 晨报控置提交时间和自动审批需求 | 晨报控置提交时间和自动审批需求 | 1 | 3 | 2018-05-23 | 2018-05-24 | 2018-05-23 | 2018-05-24 | 0.5 | 4 | 0.3125 | 0.38462
郭晶 | 报告内总股本超过千亿时，修改单位（百万级）为（十亿级） | 报告内总股本超过千亿时，修改单位（百万级）为（十亿级） | 3 | 3 | 2018-06-13 | 2018-06-15 | 2018-06-12 | 2018-06-13 | 1.875
郭晶 | 报告插件选择作者需求变更-20180614 | 报告插件选择作者需求变更 | 1 | 1 | 2018-06-15 | 2018-06-15 | 2018-06-14 | 2018-06-14 | 0.5 | 4 | 0.875 | 0.63636
郭晶 | 广发-报告模板补充 | 广发-报告模板补充 | 2 | 2 | 2018-06-21 | 2018-06-27 | 2018-06-22 | 2018-06-23 | 1.6875
郭晶 | 报告模板需求开发-需求补充 | 报告模板需求开发-需求补充 | 3 | 3 | 2018-06-25 | 2018-06-29 | 2018-06-23 | 2018-06-23 | 0.875
郭晶 | 广发-英文报告模板补充 | 广发-英文报告模板补充 | 1 | 1 | 2018-06-26 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 0.25
郭磊 | 修改公司类报告投资评级目标价 | 修改公司类报告投资评级目标价 | 1 | 1 | 2018-04-11 | 2018-04-12 | 2018-04-12 | 2018-04-11 | 0.875
郭磊 | 新华资产盈利预测 | 新华资产盈利预测 | 2 | 2 | 2018-04-12 | 2018-04-14 | 2018-04-12 | 2018-04-14 | 2
郭磊 | 2018年持仓评级规则修改 | 2018年持仓评级规则修改 | 5 | 5 | 2018-04-24 | 2018-04-28 | 2018-04-24 | 2018-05-02 | 5
郭磊 | 客户检测的行业股票研究相关sql优化 | 客户检测的行业股票研究相关sql优化 | 4 | 7 | 2018-05-04 | 2018-05-11 | 2018-05-04 | 2018-05-10 | 3.9375
郭磊 | 中海新增附件在线预览功能 | 中海新增附件在线预览功能 | 2 | 4 | 2018-05-08 | 2018-05-23 | 2018-05-22 | 2018-05-23 | 0.375 | 6 | 0.625 | 0.625
郭磊 | 合规检测-关键字检测 | 合规检测-关键字检测 | 3 | 3 | 2018-05-14 | 2018-05-18 | 2018-05-14 | 2018-05-18 | 3 | 6 | 1.3125 | 0.30435
郭磊 | 中海债券类报告撰写页评级默认展开 | 中海债券类报告撰写页评级默认展开 | 1 | 1 | 2018-06-08 | 2018-06-08 | 2018-06-07 | 2018-06-06 | 0.75 | 1 | 0.25 | 0.25
韩步 | 新增券商路演 | 新增券商路演 | 3 | 10 | 2018-05-03 | 2018-05-11 | 2018-05-03 | 2018-06-05 | 4.5 | 7 | 1.2625 | 0.21909
胡堃 | 太平资产办公审批-找回密码需求_20170726 | 太平资产办公审批-找回密码需求_20170726 |  | 5 | 2017-07-27 | 2018-08-02 | 2017-07-28 | 2017-08-10 | 0
胡堃 | 定时任务 | 定时任务 | 3 | 3 | 2018-03-30 | 2018-04-13 | 2018-03-29 | 2018-05-09 | 3.75 | 9 | 0.75 | 0.16667
胡堃 | 招商基金我的事宜都是要刷新下，或者等一会自动变，客户要处理完一件事就动态变事宜数量 | 招商基金我的事宜都是要刷新下，或者等一会自动变，客户要处理完一件事就动态变事宜数量 | 1 | 1 | 2018-04-16 | 2018-04-16 | 2018-04-16 | 2018-04-16 | 0 | 1 | 0.3125 | 1
胡堃 | 招商投研我的事宜修改 | 招商投研我的事宜修改 | 1 | 1 | 2018-04-16 | 2018-04-17 | 2018-04-16 | 2018-04-16 | 0.25 | 1 | 0.125 | 0.33333
胡堃 | 中海内部消息定制展示 | 中海内部消息定制展示 | 5 | 5 | 2018-04-30 | 2018-05-10 | 2018-05-08 | 2018-05-11 | 1.75 | 2 | 0.125 | 0.066667
胡堃 | 浦银安盛投资池主题库需求-工作流(转移) | 浦银安盛投资池主题库需求(转移) | 4 | 4 | 2018-04-30 | 2018-05-11 | 2018-04-27 | 2018-05-03 | 2.25 | 8 | 0.7 | 0.23729
胡堃 | 流程详情内容修改 | 流程详情内容修改 | 2 | 2 | 2018-05-09 | 2018-05-11 | 2018-05-16 | 2018-05-17 | 0.5
胡堃 | 邮件发送派点打分结果 | 邮件发送派点打分结果 | 1 | 4 | 2018-05-15 | 2018-05-31 | 2018-05-28 | 2018-05-30 |  | 2 | 0.1
胡堃 | 债券一级市场“交易执行”步骤批量执行需求变更 | 债券一级市场“交易执行”步骤批量执行需求变更 | 0 | 1 | 2018-05-18 | 2018-05-18 | 2018-05-19 | 2018-05-21 | 0
胡堃 | 投研交互app选人控件增加显示部门 | 投研交互app选人控件增加显示部门 | 3 | 3 | 2018-05-30 | 2018-06-05 | 2018-05-31 | 2018-06-01 | 1.25
姜明哲 | 收益分配说明模板调整 | 收益分配说明模板调整 | 4 | 4 | 2018-03-21 | 2018-04-20 | 2018-03-20 | 2018-04-02 | 4.5 | 2 | 0.5 | 0.1
姜明哲 | 14协会接口升级需求分析 | 14协会接口升级需求分析 |  | 5 | 2018-04-16 | 2018-04-20 | 2018-04-17 | 2018-04-20 | 5.25 | 14 | 1.1 | 0.17323
姜明哲 | 资管云发行端-注册上报功能升级 | 资管云发行端-注册上报功能升级 | 7 | 7 | 2018-04-23 | 2018-05-04 | 2018-04-23 | 2018-04-28 | 5.25 | 3 | 0.5 | 0.086957
姜明哲 | 资管云卖方-机构管理“统一社会信用代码”维护 | 资管云卖方-机构管理“统一社会信用代码”维护 | 2 | 2 | 2018-05-10 | 2018-05-11 | 2018-05-10 | 2018-05-11 | 1.875
柯少文 | 太平资产移动审批---“债券一级市场投标流程”优化需求 | 太平资产移动审批---“债券一级市场投标流程”优化需求 | 2.5 | 3 | 2018-04-02 | 2018-04-04 | 2018-04-03 | 2018-04-04 | 2.475
柯少文 | 太平资产移动审批--新增因私出国（境）管理需求_20180315 | 太平资产移动审批--新增因私出国（境）管理需求_20180315 | 6.5 | 16 | 2018-04-08 | 2018-04-20 | 2018-04-09 | 2018-04-20 | 6.925 | 5 | 0.6875 | 0.090312
柯少文 | 消息提示和流程撤回修改 | 消息提示和流程撤回修改 |  | 5 | 2018-04-26 | 2018-05-08 | 2018-04-28 | 2018-05-04 | 4.1875 | 1
柯少文 | 太平资产移动审批--普通债(一级市场投标)需求变更_20180502 | 太平资产移动审批--普通债(一级市场投标)需求变更_20180502 | 4 | 9 | 2018-05-03 | 2018-05-16 | 2018-05-04 | 2018-05-16 | 4.375 | 3 | 0.5 | 0.10256
柯少文 | 广发-用户英文信息维护 | 广发-用户英文信息维护 |  | 1 | 2018-05-04 | 2018-05-09 | 2018-05-07 | 2018-05-07 | 1 | 3 | 0.375 | 0.27273
柯少文 | 债券一级市场“交易执行”步骤批量执行需求变更 | 债券一级市场“交易执行”步骤批量执行需求变更 | 1 | 1 | 2018-05-18 | 2018-05-18 | 2018-05-19 | 2018-05-21 | 1.25
柯少文 | 待办标签改为定时刷新 | 待办标签改为定时刷新 | 1 | 1 | 2018-05-31 | 2018-05-31 | 2018-05-30 | 2018-05-29 | 0.75
柯少文 | 20180605_太平资产移动审批_债券一级市场需求变更 | 20180605_太平资产移动审批_债券一级市场需求变更 | 3 | 3 | 2018-06-08 | 2018-06-13 | 2018-06-07 | 2018-06-08 | 2.875 | 10 | 1.0625 | 0.26984
柯少文 | 20180605_太平资产移动审批_债券一级市场需求变更（移动端调整） | 20180605_太平资产移动审批_债券一级市场需求变更 | 1 | 3 | 2018-06-12 | 2018-06-17 | 2018-06-11 | 2018-06-12 | 1.125 | 10 | 1.0625 | 0.48571
柯少文 | 办公审批系统-权限申请模块需求变更 | 办公审批系统-权限申请模块需求变更 | 0 | 2 | 2018-06-15 | 2018-06-16 | 2018-06-15 | 2018-06-15 | 0.125 | 4 | 0.8125 | 0.86667
柯研 | 招商需求工作单-券商每天只能发起几次活动预约控制 | 招商需求工作单-券商每天只能发起几次活动预约控制 | 3 | 3 | 2018-03-28 | 2018-04-01 | 2018-03-29 | 2018-04-02 | 1.8875
柯研 | 招商需求工作单-员工活动 | 招商需求工作单-员工活动 | 5 | 5 | 2018-04-02 | 2018-04-06 | 2018-04-03 | 2018-04-08 | 2.8625 | 2 | 0.125 | 0.041841
乐成 | 前海联合券商打分修改 | 前海联合券商打分修改 | 4.5 | 5 | 2018-03-22 | 2018-04-06 | 2018-03-23 | 2018-04-08 | 4.45 | 11 | 0.55 | 0.11
乐成 | 国元证券绩效考核20180207-20180325 | 国元证券绩效考核20180207 | 2 | 3 | 2018-03-26 | 2018-04-06 | 2018-03-25 | 2018-04-08 | 0.9625 | 31 | 3.4875 | 0.78371
乐成 | 客户oracle10g数据库更换为oracle12c测试 | 客户oracle10g数据库更换为oracle12c测试 | 0.1 | 0.1 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-18 | 0.0125 | 13 | 1.325 | 0.99065
乐成 | 券商服务增加备注字段 | 券商服务增加备注字段 | 0.5 | 0.5 | 2018-04-19 | 2018-04-20 | 2018-04-19 | 2018-04-20 | 0.375
乐成 | 派点新增需求_20180419 | 派点新增需求_20180419 | 2 | 2 | 2018-04-23 | 2018-04-25 | 2018-04-23 | 2018-04-23 | 0.875
乐成 | 华泰柏瑞路演打分需求变更-20180417 | 华泰柏瑞路演打分需求变更 | 2 | 3 | 2018-04-23 | 2018-04-30 | 2018-05-02 | 2018-04-26 | 1.9875 | 13 | 1.775 | 0.47176
乐成 | wind数据源切换为oracle12c版本需求 | wind数据源切换为oracle12c版本需求 | 1 | 3 | 2018-04-24 | 2018-04-30 | 2018-04-19 | 2018-05-25 | 0.475 | 5 | 0.8125 | 0.63107
乐成 | 打分界面增加分数汇总 | 打分界面增加分数汇总 | 1 | 1 | 2018-04-24 | 2018-04-24 | 2018-04-23 | 2018-04-24 | 1 | 1 | 0.0625 | 0.058824
乐成 | 信达券商管理配置，配置打分人页面，加滚动条和全选，反选按钮 | 信达券商管理配置，配置打分人页面，加滚动条和全选，反选按钮 | 0.5 | 0.5 | 2018-04-26 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 0.5 | 1 | 0.025 | 0.047619
乐成 | 长盛研究员打分需求修改 | 长盛研究员打分需求修改 | 1 | 1 | 2018-04-30 | 2018-05-11 | 2018-05-02 | 2018-05-02 | 1 | 1 | 0.0125 | 0.012346
乐成 | 派点打分显示实时剩余点数 | 派点打分显示实时剩余点数 | 0.5 | 0.5 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 0.5 | 2 | 0.05 | 0.090909
乐成 | 研究员打分需求变更 | 研究员打分需求变更 | 2 | 2 | 2018-05-08 | 2018-05-11 | 2018-05-07 | 2018-05-08 | 1.5 | 1 | 0.0625 | 0.04
乐成 | 券商分析师打分-优化 | 券商分析师打分-优化 | 3 | 3 | 2018-05-14 | 2018-05-16 | 2018-05-14 | 2018-05-16 | 2.9375 | 2 | 0.4375 | 0.12963
乐成 | 邮件发送派点打分结果 | 邮件发送派点打分结果 | 3 | 4 | 2018-05-15 | 2018-05-31 | 2018-05-28 | 2018-05-30 | 2.5625 | 2 | 0.1 | 0.037559
乐成 | 中国人寿养老投研系统新增劵商打分 | 中国人寿养老投研系统新增劵商打分 | 20 | 20 | 2018-05-17 | 2018-06-15 | 2018-05-16 | 2018-06-26 | 14.625 | 11 | 0.4 | 0.026622
乐成 | 长盛研究员打分需求变更 | 长盛研究员打分需求变更 | 2 | 2 | 2018-05-23 | 2018-05-24 | 2018-05-22 | 2018-05-22 | 0.6875 | 2 | 0.1875 | 0.21429
乐成 | 东方证券km组织结构及用户菜单拆分需求 | 东方证券km组织结构及用户菜单拆分需求 | 5 | 5 | 2018-06-07 | 2018-06-15 | 2018-06-11 | 2018-06-13 | 2.75 | 2 | 0.25 | 0.083333
乐成 | 研究员打分新增消息提醒 | 研究员打分新增消息提醒 | 1 | 1 | 2018-06-14 | 2018-06-15 | 2018-06-13 | 2018-06-14 | 1
乐成 | 机构派点打分 | 机构派点打分 | 5 | 5 | 2018-06-18 | 2018-06-27 | 2018-06-15 | 2018-06-22 | 3.125 | 9 | 0.25 | 0.074074
乐成 | 东证期货英文报告kpi考核打分(转移) | 东证期货英文报告kpi考核打分(转移) | 3 | 4 |  |  | 2018-04-16 | 2018-04-19 | 3 | 2 | 0.05 | 0.016393
雷大为 | 基金评价 基金公司 投研团队人数【产品】 | 基金评价 基金公司 投研团队人数【产品】 | 1 | 1 | 2018-04-02 | 2018-04-08 | 2018-04-03 | 2018-04-04 | 1 | 3 | 0.1375 | 0.12088
雷大为 | 基金评价 基金公司 平均从业年限【产品】 | 基金评价 基金公司 平均从业年限【产品】 | 2 | 2 | 2018-04-02 | 2018-04-03 | 2018-04-02 | 2018-04-03 | 2.2875 | 2 | 0.1 | 0.041885
雷大为 | 基金评价 基金公司 资产类别多样性【产品】 | 基金评价 基金公司 资产类别多样性【产品】 | 0.2 | 0.2 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 0.025 | 2 | 0.1625 | 0.86667
雷大为 | FOF业绩汇总最大回撤修改 | FOF业绩汇总 | 1 | 1 | 2018-04-04 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 0.25 | 8 | 0.625 | 0.71429
雷大为 | 基金评价 基金公司 规模增长率【产品】 | 基金评价 基金公司 规模增长率【产品】 | 1 | 1 | 2018-04-04 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 0.7125 | 1 | 0.25 | 0.25974
雷大为 | 国寿安保计算器_公司成立年限 | 国寿安保计算器_公司成立年限 | 0.5 | 0.5 | 2018-04-11 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 0.5 | 3 | 0.1875 | 0.27273
雷大为 | 国寿安保计算器_基金经理平均从业年限 | 国寿安保计算器_基金经理平均从业年限 | 1 | 1 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 0.8 | 1 | 0.1625 | 0.16883
雷大为 | 国寿安保计算器_基金经理数量 | 国寿安保计算器_基金经理数量 | 1 | 1 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 1 | 5 | 0.25 | 0.2
雷大为 | 国寿安保计算器_注册资本 | 国寿安保计算器_注册资本 | 0.5 | 0.5 | 2018-04-11 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 0.5 | 2 | 0.125 | 0.2
雷大为 | 国寿安保计算器_资产规模（公募） | 国寿安保计算器_资产规模（公募） | 1 | 1 | 2018-04-12 | 2018-04-13 | 2018-04-13 | 2018-04-13 | 1 | 1 | 0.0625 | 0.058824
雷大为 | 国寿安保计算器_剔除货币基金资产规模 | 国寿安保计算器_剔除货币基金资产规模 | 1 | 1 | 2018-04-13 | 2018-04-17 | 2018-04-13 | 2018-04-16 | 0.75 | 1 | 0.125 | 0.14286
雷大为 | 基金评价 基金公司 有效规模【产品】 | 基金评价 基金公司 有效规模【产品】 | 0.5 | 0.5 | 2018-04-13 | 2018-04-13 | 2018-04-10 | 2018-04-10 | 0 | 3 | 0.3125 | 1
雷大为 | 基金经理定量指标计算 | 基金经理定量指标计算 | 2 | 2 | 2018-04-23 | 2018-04-24 | 2018-04-20 | 2018-04-24 | 1.9 | 1 | 0.0625 | 0.031847
雷大为 | 系统功能需求修改 | 系统功能需求修改 | 2 | 3 | 2018-04-27 | 2018-05-04 | 2018-04-27 | 2018-05-02 | 1.5375 | 13 | 1.7875 | 0.53759
雷大为 | 固收报告增加定性评价展示_数据接口 | 固收报告增加定性评价展示_数据接口 | 2 | 2 | 2018-05-02 | 2018-05-04 | 2018-05-03 | 2018-05-03 | 1.9375
雷大为 | 基金评价 基金公司 基金经理流动性【产品】 | 基金评价 基金公司 基金经理流动性【产品】 | 2 | 2 | 2018-05-04 | 2018-05-08 | 2018-04-10 | 2018-05-07 | 2.75
雷大为 | 组合业绩归因 | 组合业绩归因 | 3 | 3 | 2018-05-14 | 2018-05-17 | 2018-05-15 | 2018-05-21 | 4.1875 | 3 | 0.1875 | 0.042857
雷大为 | 中银-基金基本面调整 | 中银-基金基本面调整 | 1 | 1 | 2018-05-15 | 2018-05-17 | 2018-05-14 | 2018-05-15 | 1.5 | 4 | 0.4375 | 0.22581
雷大为 | 基金池入池规则配置 | 基金池入池规则配置 | 2 | 3 | 2018-05-22 | 2018-05-24 | 2018-05-22 | 2018-05-25 | 1.7375 | 27 | 6.3375 | 0.78483
雷大为 | 新增模板 | 新增模板 | 1 | 3.5 | 2018-06-06 | 2018-06-07 | 2018-06-05 | 2018-06-07 | 1 | 8 | 0.75 | 0.42857
雷大为 | 广发-英文报告附件修改 | 广发-英文报告附件修改 | 2 | 2 | 2018-06-14 | 2018-06-15 | 2018-06-14 | 2018-06-15 | 2
雷大为 | 2.2.在池股票报告到期提醒修改 | 2.2.在池股票报告到期提醒修改 | 3 | 3 | 2018-06-20 | 2018-06-25 | 2018-06-20 | 2018-06-25 | 2.5 | 2 | 0.1875 | 0.069767
雷大为 | 内部报告新增债券主体查询条件 | 内部报告新增债券主体查询条件 | 1 | 1 | 2018-06-25 | 2018-06-27 | 2018-06-25 | 2018-06-25 | 0.9375 | 8 | 0.575 | 0.38017
李健2 | 合作机构投资品统计 | 合作机构投资品统计 | 15 | 15 | 2018-03-14 | 2018-04-04 | 2018-03-19 | 2018-04-13 | 10
李健2 | 迁移临时代码转正式代码定时任务 | 迁移临时代码转正式代码定时任务 | 1 | 1 | 2018-05-03 | 2018-05-04 | 2018-05-05 | 2018-05-05 | 1 | 5 | 1.0625 | 0.51515
李健2 | 后缀添加和页面修改需求（信评） | 后缀添加和页面修改需求（信评） | 5 | 5 | 2018-05-07 | 2018-05-14 | 2018-05-08 | 2018-05-14 | 5 | 13 | 1.0625 | 0.17526
李健2 | 初评工作流(转移) | 初评工作流(转移) | 7 | 7 | 2018-05-17 | 2018-05-25 | 2018-05-16 | 2018-05-25 | 6.625 | 37 | 2.3625 | 0.26287
李杰 | 基金报告（权益与固收）修改取值_修改 | 基金报告（权益与固收）修改取值 | 1 | 1 | 2018-04-12 | 2018-04-18 | 2018-04-11 | 2018-04-11 | 0.25 | 4 | 0.4625 | 0.64912
李杰 | 系统功能需求修改 | 系统功能需求修改 | 1 | 3 | 2018-04-27 | 2018-05-04 | 2018-04-27 | 2018-05-02 | 2.25 | 13 | 1.7875 | 0.44272
李杰 | 基金池入池规则配置 | 基金池入池规则配置 | 1 | 3 | 2018-05-22 | 2018-05-24 | 2018-05-22 | 2018-05-25 | 1 | 27 | 6.3375 | 0.86371
李杰 | 数据指标修改 | 数据指标修改 | 2 | 2 | 2018-05-31 | 2018-06-01 | 2018-06-01 | 2018-05-31 | 0.875 | 3 | 0.25 | 0.22222
李雷 | 财务虚假识别修改为计划任务方式执行 -20180412 | 财务虚假识别修改为计划任务方式执行 | 1 | 1 | 2018-04-12 | 2018-04-13 | 2018-04-17 | 2018-04-17 | 0.125
李雷 | 舆情数据抓取性能优化-20180515 | 舆情数据抓取性能优化 | 1 | 1 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 0.125 | 2 | 0.5625 | 0.81818
李雷 | 利差需求修改-20180515 | 利差需求修改 | 1 | 1 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 2018-05-15 | 0.125 | 14 | 4.625 | 0.97368
李雷 | 投资池自动入池规则(转移) | 投资池自动入池规则(转移) | 5 | 5 | 2018-06-07 | 2018-06-15 | 2018-06-08 | 2018-06-14 | 3.5 | 3 | 0.275 | 0.072848
李丽华 | 另类投资-付款管理优化需求 | 另类投资-付款管理优化需求 |  | 1 | 2018-04-18 | 2018-04-19 | 2018-04-19 | 2018-04-19 | 1 | 2 | 0.0625 | 0.058824
李丽华 | 评审合规需求优化（投资端、发行端、股权） | 评审合规需求优化（投资端、发行端、股权） | 5 | 5 | 2018-04-23 | 2018-05-09 | 2018-05-02 | 2018-05-07 | 3.75 | 8 | 1.325 | 0.26108
李丽华 | 发行端-评审管理优化需求 | 发行端-评审管理优化需求 |  | 2 | 2018-04-23 | 2018-04-25 | 2018-04-24 | 2018-04-26 | 1.9375 | 1 | 0.1875 | 0.088235
李丽华 | 财务数据导入 | 财务数据导入 |  | 3 | 2018-05-10 | 2018-05-13 | 2018-05-10 | 2018-05-10 | 1 | 8 | 3.55 | 0.78022
李丽华 | 收益分配事项提醒 | 收益分配事项提醒 | 1 | 1 | 2018-05-16 | 2018-05-18 | 2018-05-17 | 2018-05-18 | 1.875 | 5 | 2.125 | 0.53125
李丽华 | 产品要素 | 产品要素 |  | 1 | 2018-05-22 | 2018-05-22 | 2018-05-23 | 2018-05-23 | 0.5625
李丽华 | 合同管理 | 合同管理 |  | 1 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 0.75
李丽华 | 产品分期 | 产品分期 |  | 4 | 2018-05-31 | 2018-06-05 | 2018-06-01 | 2018-06-05 | 2.25 | 2 | 0.125 | 0.052632
李敏捷 | TA对接展示 | TA对接展示 |  | 2 | 2018-05-22 | 2018-05-23 | 2018-05-23 | 2018-05-24 | 1.125
李晓龙 | 招商信诺投资端-（问题整理） | 招商信诺投资端-（问题整理） | 2 | 2 | 2018-04-10 | 2018-04-10 | 2018-04-10 | 2018-04-10 | 1.375 | 1 | 0.125 | 0.083333
李晓龙 | 投前要素调整 | 投前要素调整 | 3 | 3 | 2018-04-13 | 2018-04-18 | 2018-04-13 | 2018-04-18 | 3
李晓龙 | 关联方风控需求 | 关联方风控需求 | 5 | 7 | 2018-05-09 | 2018-05-23 | 2018-05-08 | 2018-05-10 | 3 | 1 | 0.1875 | 0.058824
李晓龙 | 关联方风控需求优化 | 关联方风控需求优化 | 2 | 2 | 2018-05-17 | 2018-05-18 | 2018-05-16 | 2018-05-17 | 2 | 2 | 0.375 | 0.15789
李晓龙 | 会议时间 | 会议时间 |  | 1 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 0.625 | 1 | 0.0625 | 0.090909
李肖云 | 优化需求 | 优化需求 | 8 | 8 | 2018-03-27 | 2018-04-04 | 2018-03-28 | 2018-04-09 | 7 | 3 | 2.125 | 0.23288
李肖云 | 歌斐资产合同参数功能开发 | 歌斐资产合同参数功能开发 | 4 | 4 | 2018-04-17 | 2018-04-20 | 2018-04-17 | 2018-04-19 | 3.6875 | 11 | 1.9375 | 0.34444
李肖云 | 投资者明细台账固定表头和列 | 投资者明细台账固定表头和列 | 5 | 5 | 2018-04-24 | 2018-04-27 | 2018-04-24 | 2018-04-28 | 5.125 | 1 | 1 | 0.16327
李肖云 | 产品参与定增项目情况手工维护界面开发 | 产品参与定增项目情况手工维护界面开发 |  | 1 | 2018-05-03 | 2018-05-07 | 2018-05-07 | 2018-05-07 | 0
李肖云 | 无主体指标导入和导出功能迁移 | 无主体指标导入和导出功能迁移 | 3 | 3 | 2018-05-08 | 2018-05-11 | 2018-05-10 | 2018-05-11 | 2.75 | 2 | 0.4375 | 0.13725
李肖云 | 托管人信息功能迁移 | 托管人信息功能迁移 | 1.5 | 1.5 | 2018-06-05 | 2018-06-06 | 2018-06-07 | 2018-06-08 | 1.75 | 2 | 0.25 | 0.125
李肖云 | 管理人信息功能迁移 | 管理人信息功能迁移 | 1.5 | 1.5 | 2018-06-06 | 2018-06-07 | 2018-06-11 | 2018-06-08 | 0.875 | 1 | 0.125 | 0.125
李肖云 | KETTLE监控--日志查询功能迁移 | KETTLE监控--日志查询功能迁移 | 2 | 2 | 2018-06-12 | 2018-06-13 | 2018-06-14 | 2018-06-15 | 3 | 2 | 0.25 | 0.076923
李肖云 | 指标使用日志查询功能迁移 | 指标使用日志查询功能迁移 | 1 | 1 | 2018-06-14 | 2018-06-15 | 2018-06-13 | 2018-06-19 | 1 | 2 | 0.25 | 0.2
刘鸿基 | 20180419会议纪要需求修改 | 20180419会议纪要需求修改 | 5 | 6 | 2018-04-20 | 2018-04-27 | 2018-04-20 | 2018-04-26 | 5 | 5 | 1.4375 | 0.2233
刘鸿基 | 信评数据源管理 | 信评数据源管理 | 10 | 15 | 2018-04-30 | 2018-05-11 | 2018-04-27 | 2018-05-11 | 11.25 | 25 | 3.1875 | 0.22078
刘鸿基 | 主体信用评级部分 | 主体信用评级部分 | 6 | 6 | 2018-05-14 | 2018-05-22 | 2018-05-14 | 2018-05-18 | 5.75 | 22 | 2.575 | 0.30931
刘鸿基 | 对接广发银行企业级客户信息应用平台 | 对接广发银行企业级客户信息应用平台 | 10 | 10 | 2018-05-21 | 2018-06-01 | 2018-05-21 | 2018-05-25 | 5 | 2 | 0.0125 | 0.0024938
刘鸿基 | 对接反洗钱业务系统 | 对接反洗钱业务系统 | 5 | 5 | 2018-05-28 | 2018-06-01 | 2018-05-28 | 2018-05-29 | 2 | 1 | 0.05 | 0.02439
刘鸿基 | 持续管理(转移) | 持续管理(转移) | 4 | 7 | 2018-05-28 | 2018-06-05 | 2018-05-28 | 2018-06-08 | 7.5 | 16 | 0.85 | 0.1018
刘靖宇 | 关系型数据源配置功能迁移 | 关系型数据源配置功能迁移 | 2 | 2 | 2018-04-12 | 2018-04-13 | 2018-04-12 | 2018-04-13 | 3 | 4 | 0.5 | 0.14286
刘靖宇 | 新框架数据库表管理功能迁移 | 新框架数据库表管理功能迁移 | 5 | 5 | 2018-04-16 | 2018-04-20 | 2018-04-17 | 2018-04-23 | 4.875 | 22 | 1.125 | 0.1875
刘靖宇 | 数据列表和数据检索功能迁移 | 数据列表和数据检索功能迁移 | 5 | 5 | 2018-04-23 | 2018-04-28 | 2018-04-24 | 2018-05-02 | 5 | 2 | 0.125 | 0.02439
刘靖宇 | 数据库表信息导入功能迁移 | 数据库表信息导入功能迁移 | 3 | 3 | 2018-05-07 | 2018-05-11 | 2018-05-10 | 2018-05-14 | 2
刘君城 | 民生加银内部报告邮件发送功能 | 民生加银内部报告邮件发送功能 | 3 | 3 | 2018-03-29 | 2018-04-10 | 2018-03-30 | 2018-04-08 | 3 | 4 | 0.6875 | 0.18644
刘君城 | 华泰柏瑞报告入库审批页面更改-20180404 | 华泰柏瑞报告入库审批页面更改 | 2 | 2 | 2018-04-05 | 2018-04-10 | 2018-04-08 | 2018-04-08 | 1 | 1 | 0.025 | 0.02439
刘君城 | 东证期货sirm添加英文报告类型(转移) | 东证期货sirm添加英文报告类型(转移) | 5 | 5 | 2018-04-09 | 2018-04-13 | 2018-04-09 | 2018-04-13 | 4.375
刘君城 | 报告流程增加质量复审配置。 | 报告流程增加质量复审配置。 | 2 | 2 | 2018-04-13 | 2018-04-15 | 2018-04-12 | 2018-04-12 | 0.8125 | 2 | 0.0625 | 0.071429
刘君城 | 内部撰写报告修改 | 内部撰写报告修改 | 1 | 3 | 2018-04-16 | 2018-04-18 | 2018-04-16 | 2018-04-17 | 0.9375
刘君城 | 内部报告流程定制 | 内部报告流程定制 | 2 | 2 | 2018-04-18 | 2018-04-20 | 2018-04-18 | 2018-04-19 | 1.375 | 2 | 0.125 | 0.083333
刘君城 | 内部报告增加批量审批功能 | 内部报告增加批量审批功能 | 1 | 4 | 2018-04-18 | 2018-04-23 | 2018-04-18 | 2018-04-20 | 0.25
刘君城 | 内部报告入库后，邮件提醒模版上加上该篇报告的查看链接 | 内部报告入库后，邮件提醒模版上加上该篇报告的查看链接 | 1 | 1 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 1 | 1 | 0.125 | 0.11111
刘君城 | 中银国际销售需求-报告插件0419 | 中银国际销售需求-报告插件0419 | 1 | 4 | 2018-04-20 | 2018-04-26 | 2018-04-20 | 2018-04-26 | 0.75 | 25 | 1.35 | 0.64286
刘君城 | 信评内部报告修改需求-20180423 | 信评内部报告修改需求 | 1 | 1 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-24 | 1 | 11 | 0.4625 | 0.31624
刘君城 | 港股报告-国泰君安 | 港股报告-国泰君安 | 0 | 2 | 2018-04-24 | 2018-04-25 | 2018-04-23 | 2018-04-24
刘君城 | 第一作者的需求 | 第一作者的需求 | 0.5 | 3 | 2018-04-25 | 2018-04-27 | 2018-04-26 | 2018-04-26 | 0.25 | 1 | 0.125 | 0.33333
刘君城 | 信评内部报告修改需求-20180425 | 信评内部报告修改需求 | 1 | 2 | 2018-04-25 | 2018-05-02 | 2018-04-25 | 2018-05-02 | 0.75 | 11 | 0.4625 | 0.38144
刘君城 | 入库内部报告修改 | 入库内部报告修改 | 2 | 2 | 2018-04-26 | 2018-04-27 | 2018-04-26 | 2018-04-27 | 2 | 4 | 0.4375 | 0.17949
刘君城 | 内部报告查询页面修改 | 内部报告查询页面修改 | 0.5 | 3 | 2018-04-30 | 2018-05-03 | 2018-04-27 | 2018-04-28
刘君城 | 投研平台周月报需求(转移) | 投研平台周月报需求(转移) | 3 | 3 | 2018-05-02 | 2018-05-04 | 2018-05-02 | 2018-05-04 | 2.875
刘君城 | 内部报告修改 | 内部报告修改 | 1 | 7 | 2018-05-04 | 2018-05-18 | 2018-05-04 | 2018-05-18 | 0.1875 | 29 | 5.25 | 0.96552
刘君城 | 报告统计 | 报告统计 | 2 | 2 | 2018-05-07 | 2018-05-18 | 2018-05-07 | 2018-05-18 | 2 | 6 | 0.4375 | 0.17949
刘君城 | 客户检测的内部报告相关sql优化 | 客户检测的内部报告相关sql优化 | 4 | 4 | 2018-05-08 | 2018-05-11 | 2018-05-10 | 2018-05-11 | 2.375
刘君城 | 中海新增附件在线预览功能 | 中海新增附件在线预览功能 | 2 | 4 | 2018-05-08 | 2018-05-23 | 2018-05-22 | 2018-05-23 | 1.25 | 6 | 0.625 | 0.33333
刘君城 | 投资池&报告流程定制提醒-内部报告 | 投资池&报告流程定制提醒 | 2 | 2 | 2018-05-10 | 2018-05-18 | 2018-05-17 | 2018-05-18 | 1.6875 | 1 | 0.25 | 0.12903
刘君城 | 长盛内部报告提醒需求 | 长盛内部报告提醒需求 | 3 | 3 | 2018-05-14 | 2018-05-17 | 2018-05-14 | 2018-05-16 | 2.875 | 3 | 0.3125 | 0.098039
刘君城 | 投资池&报告流程定制提醒-20180522 | 投资池&报告流程定制提醒 | 1 | 1 | 2018-05-23 | 2018-05-24 | 2018-05-22 | 2018-05-23 | 0.625 | 1 | 0.25 | 0.28571
刘君城 | 报告统计-20180531 | 报告统计 | 0.5 | 2.5 | 2018-06-01 | 2018-06-05 | 2018-06-01 | 2018-06-04 | 0.25 | 6 | 0.4375 | 0.63636
刘君城 | 云估值-增加redis处理（插件登录及页面注册） | 云估值-增加redis处理（插件登录及页面注册） | 2 | 2 | 2018-06-12 | 2018-06-13 | 2018-06-12 | 2018-06-13 | 2
罗强 | 报告模板更新 | 报告模板更新 | 5 | 6 | 2018-04-10 | 2018-04-13 | 2018-04-10 | 2018-04-11 | 3.8125 | 8 | 0.75 | 0.16438
罗强 | 报告模板更新-需求变更 | 报告模板更新-需求变更 | 2 | 2 | 2018-04-16 | 2018-04-18 | 2018-04-16 | 2018-04-16 | 1
罗强 | 云估值-插件 | 云估值-插件 | 5 | 15 | 2018-04-16 | 2018-04-27 | 2018-04-17 | 2018-04-25 | 3.75
罗强 | 修改模板需求_2 | 修改模板需求_2 | 2 | 2 | 2018-04-18 | 2018-04-28 | 2018-04-17 | 2018-04-25 | 1.9375 | 3 | 0.1 | 0.04908
罗强 | 债券分类下的4个模板新增表格数据更新 | 债券分类下的4个模板新增表格数据更新 | 2 | 2 | 2018-04-26 | 2018-04-27 | 2018-04-26 | 2018-04-26 | 1
罗强 | 报告模板首页logo提高清晰度 | 报告模板首页logo提高清晰度 | 1 | 1 | 2018-04-28 | 2018-04-29 | 2018-05-03 | 2018-05-03 | 0.5 | 1 | 0.0375 | 0.069767
罗强 | 云模型插件升级优化 | 云模型插件升级优化 | 6 | 18 | 2018-05-03 | 2018-05-10 | 2018-05-03 | 2018-05-08 | 3.0625 | 3 | 0.4375 | 0.125
罗强 | 公司模板和行业模板需求 | 公司模板和行业模板需求 | 3 | 3 | 2018-05-14 | 2018-05-24 | 2018-05-15 | 2018-05-24 | 4.25 | 28 | 1.3375 | 0.23937
罗强 | 行业报告模板无子报告需求 | 行业报告模板无子报告需求 | 3 | 3 | 2018-05-16 | 2018-05-18 | 2018-05-16 | 2018-05-18 | 3 | 6 | 2.3625 | 0.44056
罗强 | 银河基金sirm内部报告模板修改 | 银河基金sirm内部报告模板修改 | 2 | 4 | 2018-05-24 | 2018-05-25 | 2018-05-24 | 2018-05-25 | 1.125 | 1 | 0.25 | 0.18182
罗强 | 广发-英文报告模板开发和解析-尾页声明变更 | 广发-英文报告模板开发和解析 | 2 | 10 | 2018-05-24 | 2018-06-05 | 2018-05-24 | 2018-05-31 | 2.75 | 22 | 1.25 | 0.3125
罗强 | 银河基金sirm报告模板修改优化 | 银河基金sirm报告模板修改优化 | 2 | 2 | 2018-06-15 | 2018-06-15 | 2018-06-14 | 2018-06-14 | 1 | 2 | 0.125 | 0.11111
罗天龙 | 组合管理指标函数优化与改造 | 组合管理指标函数优化与改造 | 5 | 12 | 2018-04-16 | 2018-04-20 | 2018-04-16 | 2018-04-20 | 5 | 5 | 0.375 | 0.069767
骆梦茹 | v3.1-项目汇总查询优化 | v3.1-项目汇总查询优化 | 1.5 | 2 | 2018-05-31 | 2018-06-01 | 2018-05-31 | 2018-06-01 | 1.625 | 2 | 0.25 | 0.13333
骆梦茹 | v3.2-外部项目立项优化 | v3.2-外部项目立项优化 | 7.5 | 8 | 2018-06-06 | 2018-06-22 | 2018-06-06 | 2018-06-22 | 7.875 | 5 | 0.75 | 0.086957
满豪 | 财务简表&财务分析广发银行迁移 | 财务简表&财务分析广发银行迁移 | 5 | 5 | 2018-04-12 | 2018-04-18 | 2018-04-13 | 2018-04-16 | 2.775 | 16 | 2.025 | 0.42188
满豪 | 管理员页面技术支持页面修改(转移) | 管理员页面技术支持页面修改(转移) | 2 | 2 | 2018-06-07 | 2018-06-08 | 2018-06-08 | 2018-06-07 | 1 | 1 | 0.875 | 0.46667
孟伟芳 | ST股、联合覆盖申请控制 | ST股、联合覆盖申请控制 | 2 | 2 | 2018-04-02 | 2018-04-02 | 2018-03-28 | 2018-04-02 | 2.375
孟伟芳 | 路演申请中的路演时间修改 | 路演申请中的路演时间修改 | 1 | 1 | 2018-04-03 | 2018-04-03 | 2018-04-02 | 2018-04-02 | 0.25
孟伟芳 | 增加大额持仓内容检测提醒 | 增加大额持仓内容检测提醒 | 2 | 2 | 2018-04-03 | 2018-04-04 | 2018-04-02 | 2018-04-03 | 1.25
孟伟芳 | 路演申请展示时间修改 | 路演申请展示时间修改 | 2 | 2 | 2018-04-08 | 2018-04-10 | 2018-04-03 | 2018-04-08 | 1.625
孟伟芳 | 检索所有审批功能，优化速度 | 检索所有审批功能，优化速度 | 3 | 3 | 2018-04-10 | 2018-04-13 | 2018-04-08 | 2018-04-13 | 1.375
孟伟芳 | 银行组报告提交及审核时对EPS检测的计算公式进行调整 | 银行组报告提交及审核时对EPS检测的计算公式进行调整 | 1 | 1 | 2018-04-12 | 2018-04-13 | 2018-04-11 | 2018-04-12 | 2
孟伟芳 | 如果出差、联合调研等流程超过一个月，自动终止 | 如果出差、联合调研等流程超过一个月，自动终止 | 1 | 1 | 2018-04-12 | 2018-04-16 | 2018-04-12 | 2018-04-16 | 1.75
孟伟芳 | IPO流程，由提交人选择大组长 | IPO流程，由提交人选择大组长 | 2 | 2 | 2018-04-23 | 2018-04-25 | 2018-04-20 | 2018-04-23 | 1.625
孟伟芳 | 跨墙信息列表页面增加姓名查询 | 跨墙信息列表页面增加姓名查询 | 2 | 2 | 2018-04-30 | 2018-05-03 | 2018-05-02 | 2018-05-02 | 0.25
孟伟芳 | 回墙信息通知修改，修改后第一时间发送通知 | 回墙信息通知修改，修改后第一时间发送通知 | 2 | 2 | 2018-04-30 | 2018-05-04 | 2018-04-27 | 2018-04-27 | 1
孟伟芳 | 短信发送功能，金工组短信增加关联报告 | 短信发送功能，金工组短信增加关联报告 | 2 | 2 | 2018-05-03 | 2018-05-09 | 2018-05-03 | 2018-05-03 | 0.375
孟伟芳 | 修改回墙通知消息 | 修改回墙通知消息 | 1 | 1 | 2018-05-03 | 2018-05-04 | 2018-05-02 | 2018-05-02 | 0.75
孟伟芳 | 新增发布研究报告数据需求 | 新增发布研究报告数据需求 | 10 | 10 | 2018-05-07 | 2018-05-31 | 2018-04-16 | 2018-05-24 | 11.625
孟伟芳 | 驳回页面修改，增加低级错误录入（WEB.PAD） | 驳回页面修改，增加低级错误录入（WEB.PAD） | 2 | 2 | 2018-05-09 | 2018-05-10 | 2018-05-07 | 2018-05-09 | 2
孟伟芳 | 金工组报告&债券日报，增加申明勾选 | 金工组报告&债券日报，增加申明勾选 | 2 | 2 | 2018-05-10 | 2018-05-14 | 2018-05-08 | 2018-05-09 | 1
孟伟芳 | 流程超过五个工作日自动停止功能增加一个例外功能 | 流程超过五个工作日自动停止功能增加一个例外功能 | 1 | 1 | 2018-05-14 | 2018-05-14 | 2018-05-11 | 2018-05-11 | 0.375
孟伟芳 | 流程步骤短信提醒 | 流程步骤短信提醒 | 3 | 3 | 2018-05-17 | 2018-05-18 | 2018-05-16 | 2018-05-17 | 3
孟伟芳 | 专家提交及审批流程 | 专家提交及审批流程 | 2 | 2 | 2018-05-18 | 2018-05-30 | 2018-05-29 | 2018-06-01 | 3
孟伟芳 | 专家库增加导出功能 | 专家库增加导出功能 | 2 | 2 | 2018-05-18 | 2018-05-31 | 2018-06-01 | 2018-06-01 | 1
孟伟芳 | 邀请专家库中的专家领域 | 邀请专家库中的专家领域 | 2 | 2 | 2018-05-18 | 2018-05-24 | 2018-05-28 | 2018-05-28 | 0.75
孟伟芳 | 联合调研查询排序功能 | 联合调研查询排序功能 | 2 | 2 | 2018-05-18 | 2018-05-28 | 2018-05-28 | 2018-05-28 | 0.25
孟伟芳 | 禁止库中的股票，不允许提交公司报告 | 禁止库中的股票，不允许提交公司报告 | 1 | 1 | 2018-05-24 | 2018-05-24 | 2018-05-24 | 2018-05-23 | 0.125
孟伟芳 | 研报相关统计修改 | 研报需求修改 | 1 | 1 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 0.625
孟伟芳 | IPO流程修改，增加重新审批功能 | IPO流程修改，增加重新审批功能 | 2 | 2 | 2018-06-05 | 2018-06-08 | 2018-06-05 | 2018-06-06 | 1.875
孟伟芳 | Matrix系统对接，联系人删除功能 | Matrix系统对接，联系人删除功能 | 1 | 1 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 2018-06-06 | 0.125
孟伟芳 | 推送电话会议相关内容给Matrix | 推送电话会议相关内容给Matrix | 3 | 3 | 2018-06-08 | 2018-06-13 | 2018-06-07 | 2018-06-07 | 0.5
孟伟芳 | Matrix系统中批量审批研报需求推送失败 | Matrix系统中批量审批研报需求推送失败 | 2 | 2 | 2018-06-11 | 2018-06-15 | 2018-06-12 | 2018-06-12 | 0.5
孟伟芳 | 路演预约功能修复 | 路演预约功能修复 | 1 | 1 | 2018-06-11 | 2018-06-13 | 2018-06-11 | 2018-06-12 | 1
孟伟芳 | 宏观重要报告改为3选2 | 宏观重要报告改为3选2 | 1 | 1 | 2018-06-13 | 2018-06-13 | 2018-06-08 | 2018-06-11 | 1
孟伟芳 | Matirx系统失败后重新推送数据 | Matirx系统失败后重新推送数据 | 2 | 2 | 2018-06-13 | 2018-06-18 | 2018-06-13 | 2018-06-14 | 2
孟伟芳 | 出差、调研流程检测审批时间，超时发送提醒 | 出差、调研流程检测审批时间，超时发送提醒 | 2 | 2 | 2018-06-14 | 2018-06-22 | 2018-06-14 | 2018-06-15 | 1.375
孟伟芳 | 增加股价异动 | 增加股价异动 | 3 | 3 | 2018-06-14 | 2018-06-27 | 2018-06-22 | 2018-06-26 | 3
孟伟芳 | 工作底稿说明修改 | 工作底稿说明修改 | 1 | 1 | 2018-06-19 | 2018-06-20 | 2018-06-14 | 2018-06-14 | 0.125
孟伟芳 | 金工组报告检查限制清单 | 金工组报告检查限制清单 | 1 | 1 | 2018-06-21 | 2018-06-26 | 2018-06-21 | 2018-06-21 | 0.5
孟伟芳 | 研报需求调整功能，报告数量，报告问题，警示函 | 研报需求调整功能，报告数量，报告问题，警示函 | 3 | 3 | 2018-06-22 | 2018-06-26 | 2018-06-19 | 2018-06-21 | 2.5
牛皖利 | 研究服务申请增加手机端功能 | 研究服务申请增加手机端功能 | 3 | 7 | 2018-03-30 | 2018-04-04 | 2018-03-30 | 2018-04-10 | 3.6562 | 16 | 0.3875 | 0.095827
牛皖利 | 进门财经审核增加手机展示 | 进门财经审核增加手机展示 | 3 | 7 | 2018-04-04 | 2018-04-15 | 2018-04-03 | 2018-04-12 | 2.8438
牛皖利 | 太平资产移动审批--新增因私出国（境）管理需求_20180315 | 太平资产移动审批--新增因私出国（境）管理需求_20180315 | 1 | 16 | 2018-04-08 | 2018-04-20 | 2018-04-09 | 2018-04-20 | 0.5 | 5 | 0.6875 | 0.57895
牛皖利 | 进门财经审核手机端合规展示 | 进门财经审核手机端合规展示 | 1 | 2 | 2018-04-13 | 2018-04-20 | 2018-04-12 | 2018-04-13 | 1.1875
牛皖利 | 手机端ipo分配人页面修改流程调整 | 手机端ipo分配人页面修改流程调整 | 0.5 | 4.5 | 2018-04-23 | 2018-04-24 | 2018-04-23 | 2018-04-24 | 0.5
牛皖利 | 投研交互app修改密码 | 投研交互app修改密码 | 2 | 5 | 2018-06-20 | 2018-06-21 | 2018-06-20 | 2018-06-20 | 0 | 7 | 1.875 | 1
裴磊磊 | 研究服务申请增加手机端功能 | 研究服务申请增加手机端功能 | 1 | 7 | 2018-03-30 | 2018-04-04 | 2018-03-30 | 2018-04-10 |  | 16 | 0.3875
裴磊磊 | 进门财经审核增加手机展示 | 进门财经审核增加手机展示 | 0.5 | 7 | 2018-04-04 | 2018-04-15 | 2018-04-03 | 2018-04-12
彭威 | 业务页面开发-修改 | 信评移动端开发 | 4 | 5 | 2018-05-14 | 2018-05-17 | 2018-05-24 | 2018-05-24 | 0.125 | 67 | 8.6062 | 0.98568
彭忠宁 | 微信公众号-舆情信息&主体识别 | 微信公众号-舆情信息&主体识别 | 3 | 3 | 2018-04-02 | 2018-04-04 | 2018-04-04 | 2018-04-09 | 2.25 | 5 | 0.375 | 0.14286
彭忠宁 | 日常工作-路演、活动 | 日常工作-路演、活动 | 10 | 20 | 2018-04-09 | 2018-04-22 | 2018-03-26 | 2018-04-24 | 10 | 12 | 1.9375 | 0.1623
彭忠宁 | 日常工作-路演、活动-变更 | 日常工作-路演、活动 | 5 | 8 | 2018-05-07 | 2018-05-11 | 2018-05-07 | 2018-05-08 | 2 | 12 | 1.9375 | 0.49206
彭忠宁 | 舆情信息优化 | 舆情信息优化 | 1 | 1 | 2018-05-18 | 2018-05-20 | 2018-05-18 | 2018-05-18 | 1
秦胜 | 审批报告时点击通过弹框提醒 | 审批报告时点击通过弹框提醒 | 0.5 | 1 | 2018-04-11 | 2018-04-12 | 2018-04-11 | 2018-04-11 | 0.5
秦胜 | 债券主体报告功能优化_20180411 | 债券主体报告功能优化_20180411 | 2 | 3 | 2018-04-12 | 2018-04-16 | 2018-04-12 | 2018-04-13 | 2 | 1 | 0.025 | 0.012346
秦胜 | 内部撰写报告修改 | 内部撰写报告修改 | 2 | 3 | 2018-04-16 | 2018-04-18 | 2018-04-16 | 2018-04-17 | 2
秦胜 | 内部报告增加批量审批功能 | 内部报告增加批量审批功能 | 3 | 4 | 2018-04-18 | 2018-04-23 | 2018-04-18 | 2018-04-20 | 3
秦胜 | 港股报告-国泰君安 | 港股报告-国泰君安 | 2 | 2 | 2018-04-24 | 2018-04-25 | 2018-04-23 | 2018-04-24 | 2
秦胜 | 第一作者的需求 | 第一作者的需求 | 2.5 | 3 | 2018-04-25 | 2018-04-27 | 2018-04-26 | 2018-04-26 | 2 | 1 | 0.125 | 0.058824
秦胜 | 模板提取标题 | 模板提取标题 | 1 | 1 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 0.875
秦胜 | 内部报告查询页面修改 | 内部报告查询页面修改 | 2.5 | 3 | 2018-04-30 | 2018-05-03 | 2018-04-27 | 2018-04-28 | 1.125
秦胜 | 内部报告的行业评级取消与行业研究模块的关联 | 内部报告的行业评级取消与行业研究模块的关联 | 2 | 2 | 2018-05-02 | 2018-05-04 | 2018-05-02 | 2018-05-03 | 1.375 | 3 | 0.625 | 0.3125
秦胜 | 内部报告修改 | 内部报告修改 | 6 | 7 | 2018-05-04 | 2018-05-18 | 2018-05-04 | 2018-05-18 | 5.25 | 29 | 5.25 | 0.5
秦胜 | 内部报告修改 | 内部报告修改 | 2 | 2 | 2018-05-10 | 2018-05-11 | 2018-05-14 | 2018-05-11 | 1 | 2 | 0.75 | 0.42857
秦胜 | 中海撰写报告标题自动生成 | 中海撰写报告标题自动生成 | 1 | 1 | 2018-05-29 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 1 | 1 | 0.25 | 0.2
秦胜 | 报告统计-20180531 | 报告统计 | 2 | 2.5 | 2018-06-01 | 2018-06-05 | 2018-06-01 | 2018-06-04 | 1.375 | 6 | 0.4375 | 0.24138
秦胜 | 手机合规后台接口协助 | 手机合规后台接口协助 | 1 | 2 | 2018-06-06 | 2018-06-07 | 2018-06-06 | 2018-06-06 | 1 | 1 | 0.125 | 0.11111
秦胜 | 报告查询界面修改 | 报告查询界面修改 | 2.8 | 2.8 | 2018-06-15 | 2018-06-22 | 2018-06-15 | 2018-06-25 | 2.8125 | 3 | 0.375 | 0.11765
秦胜 | 控制报告类型是否允许写一般类型报告 | 控制报告类型是否允许写一般类型报告 | 2 | 2 | 2018-06-25 | 2018-06-27 | 2018-06-26 | 2018-06-25 | 0.75 | 1 | 0.25 | 0.25
秦新欣 | 派点打分查询页面增加查询条件 | 派点打分查询页面增加查询条件 | 1 | 1 | 2018-06-27 | 2018-06-28 | 2018-06-26 | 2018-06-29 | 2.125
商振 | 债券负面新闻展示 | 债券负面新闻展示 | 4 | 5 | 2018-05-28 | 2018-06-01 | 2018-05-28 | 2018-06-04 | 5.25 | 3 | 0.625 | 0.10638
商振 | 20180607用户测试修改 | 20180607用户测试修改 | 2 | 2 | 2018-06-08 | 2018-06-12 | 2018-06-08 | 2018-06-08 | 0.75 | 5 | 0.375 | 0.33333
尚宇 | 加签发起时意见展示 | 加签发起时意见展示 | 1.5 | 1.5 | 2018-03-29 | 2018-04-02 | 2018-04-02 | 2018-04-03 | 1.625 | 1 | 0.25 | 0.13333
尚宇 | 关联流程 | 关联流程 | 1 | 2 | 2018-04-02 | 2018-04-04 | 2018-04-04 | 2018-04-11 | 2.25 | 6 | 1.0625 | 0.32075
尚宇 | 邮件添加链接 | 邮件添加链接 | 1.5 | 1.5 | 2018-04-12 | 2018-04-13 | 2018-04-12 | 2018-04-13 | 1.5 | 7 | 2.375 | 0.6129
尚宇 | 钉钉端流程优化(转移) | 钉钉端流程优化(转移) | 1.5 | 1.5 | 2018-04-16 | 2018-04-17 | 2018-04-16 | 2018-04-16 | 0.875 | 8 | 2.125 | 0.70833
尚宇 | 资金追加提取页面添加要素 | 资金追加提取页面添加要素 | 1 | 1 | 2018-04-17 | 2018-04-20 | 2018-04-16 | 2018-04-17 | 0.125 | 2 | 0.25 | 0.66667
尚宇 | 添加备注输入框 | 添加备注输入框 | 2 | 2 | 2018-04-23 | 2018-04-24 | 2018-04-23 | 2018-04-26 | 2.5 | 4 | 0.5 | 0.16667
尚宇 | 全流程展示处理人 | 全流程展示处理人 | 3 | 3 | 2018-04-30 | 2018-05-04 | 2018-04-27 | 2018-05-04 | 5 | 13 | 4.125 | 0.45205
尚宇 | 页面细节调整 | 页面细节调整 | 1 | 1 | 2018-05-07 | 2018-05-10 | 2018-05-07 | 2018-05-10 | 1.4375 | 3 | 0.125 | 0.08
尚宇 | 钉钉端控件优化(转移) | 钉钉端控件优化(转移) | 3 | 3 | 2018-05-14 | 2018-05-18 | 2018-05-11 | 2018-05-18 | 3.875 | 1 | 0.75 | 0.16216
尚宇 | 任务邮件添加链接 | 任务邮件添加链接 | 2 | 2 | 2018-05-28 | 2018-05-29 | 2018-05-25 | 2018-05-29 | 1.25 | 3 | 1.5 | 0.54545
尚宇 | 机构控件修改 | 机构控件修改 | 1 | 1 | 2018-05-29 | 2018-06-01 | 2018-05-28 | 2018-05-29 | 1.125 | 1 | 0.5 | 0.30769
尚宇 | 钉钉的后台管理系统添加过滤器(转移) | 钉钉的后台管理系统添加过滤器(转移) | 1 | 1 | 2018-06-07 | 2018-06-08 | 2018-06-06 | 2018-06-06 | 0.5 | 1
尚宇 | 系统报告功能修改 | 系统报告功能修改 | 1.5 | 3 | 2018-06-14 | 2018-06-20 | 2018-06-13 | 2018-06-19 | 2.25 | 3 | 0.5625 | 0.2
尚宇 | 定量评价指标展示列修改 | 定量评价指标展示列修改 | 2 | 2 | 2018-06-14 | 2018-06-15 | 2018-06-13 | 2018-06-13 | 1 | 4 | 1.5 | 0.6
尚宇 | 已完成列表数据不全 | 已完成列表数据不全 | 1 | 1 | 2018-06-14 | 2018-06-22 | 2018-06-20 | 2018-06-21 | 0.75 | 2 | 0.75 | 0.5
沈体龙 | 功能优化修复 | 问题修复优化 | 2 | 2 | 2018-04-03 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2 | 14 | 5.5 | 0.73333
沈体龙 | 移动端接口开发 | 移动端接口开发 | 1 | 10 | 2018-04-10 | 2018-04-16 | 2018-04-10 | 2018-04-16 | 2 | 4 | 1.75 | 0.46667
沈体龙 | 移动端-券商观点接口开发 | 移动端-券商观点接口开发 | 5 | 6 | 2018-04-25 | 2018-05-04 | 2018-04-26 | 2018-05-04 | 5 | 4 | 1.75 | 0.25926
宋博文 | 【方正证券】客户管理需求分析文档 | 【方正证券】客户管理需求分析文档 | 5 | 5 | 2018-05-22 | 2018-05-28 | 2018-05-21 | 2018-06-06 | 7.375 | 49 | 3.25 | 0.30588
宋博文 | 工作申请功能添加客户类型列以及查询条件 | 工作申请功能添加客户类型列以及查询条件 | 2 | 2 | 2018-05-24 | 2018-05-29 | 2018-05-29 | 2018-06-01 | 1 | 2 | 0.125 | 0.11111
宋博文 | 报告撰写数量统计加入晨会信息 | 报告撰写数量统计加入晨会信息 | 2 | 2 | 2018-05-30 | 2018-06-01 | 2018-06-01 | 2018-06-01 | 1 | 3 | 1.25 | 0.55556
宋博文 | 研究员打分 | 研究员打分 | 4 | 4 | 2018-06-05 | 2018-06-27 | 2018-06-05 | 2018-06-13 | 4.125 | 8 | 1.625 | 0.28261
宋博文 | 【方正证券】客户管理需求增加区域列 | 【方正证券】客户管理需求分析文档 | 0.5 | 0.5 | 2018-06-07 | 2018-06-08 | 2018-06-08 | 2018-06-13 | 0.625 | 49 | 3.25 | 0.83871
孙煜 | 移动端接口开发 | 移动端接口开发 | 4 | 10 | 2018-04-10 | 2018-04-16 | 2018-04-10 | 2018-04-16 | 4.75 | 4 | 1.75 | 0.26923
孙煜 | KMV模型功能迁移 | KMV模型功能迁移 | 5 | 5 | 2018-04-16 | 2018-04-20 | 2018-04-17 | 2018-04-20 | 2.4375 | 7 | 0.5 | 0.17021
孙煜 | 发行人负面新闻增加筛选过滤 | 发行人负面新闻增加筛选过滤 | 1 | 1 | 2018-04-19 | 2018-04-20 | 2018-04-19 | 2018-04-19 | 1 | 2 | 0.375 | 0.27273
孙煜 | 20180419会议纪要需求修改 | 20180419会议纪要需求修改 | 1 | 6 | 2018-04-20 | 2018-04-27 | 2018-04-20 | 2018-04-26 |  | 5 | 1.4375
孙煜 | 债券模块初始化评级存量数据 | 债券模块初始化评级存量数据 | 3 | 3 | 2018-04-23 | 2018-05-03 | 2018-04-23 | 2018-04-26 | 2 | 5 | 0.75 | 0.27273
孙煜 | 模型配置 | 模型配置 | 1 | 11 | 2018-04-27 | 2018-05-11 | 2018-04-26 | 2018-05-11 | 0.875 | 28 | 2.975 | 0.77273
孙煜 | 信评数据源管理 | 信评数据源管理 | 5 | 15 | 2018-04-30 | 2018-05-11 | 2018-04-27 | 2018-05-11 | 0.475 | 25 | 3.1875 | 0.87031
孙煜 | 主体评级_1 | 主体评级_1 | 10 | 10 | 2018-04-30 | 2018-05-18 | 2018-04-28 | 2018-05-17 | 9.9375 | 21 | 3.1 | 0.23778
孙煜 | 债券模块初始化评级存量数据-20180514 | 债券模块初始化评级存量数据 | 1 | 1 | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-11 | 0.625 | 5 | 0.75 | 0.54545
孙煜 | 债券模块初始化评级存量数据-20180518 | 债券模块初始化评级存量数据 | 1 | 1 | 2018-05-18 | 2018-05-21 | 2018-05-18 | 2018-05-18 | 1 | 5 | 0.75 | 0.42857
孙煜 | 我的评审任务 | 我的评审任务 | 6 | 6 | 2018-05-21 | 2018-06-01 | 2018-05-22 | 2018-06-01 | 5.875 | 5 | 0.8375 | 0.12477
唐伟 | 去掉晨会评论 | 去掉晨会评论 | 0.5 | 0.5 | 2018-05-31 | 2018-05-31 | 2018-05-31 | 2018-05-31 | 0.0625
童昌 | 恒大信评-评级流程管理 | 恒大信评-评级流程管理 | 5 | 5 | 2018-05-18 | 2018-05-27 | 2018-05-21 | 2018-05-25 | 3.6875 | 15 | 1.4375 | 0.28049
童昌 | 债券负面新闻展示 | 债券负面新闻展示 | 1 | 5 | 2018-05-28 | 2018-06-01 | 2018-05-28 | 2018-06-04 | 0.125 | 3 | 0.625 | 0.83333
童昌 | 产品版本由2.2升级到2.3 | 产品版本由2.2升级到2.3 | 2 | 2 | 2018-06-11 | 2018-06-13 | 2018-06-12 | 2018-06-13 | 1.1875 | 36 | 2.925 | 0.71125
童昌 | 恒大信评-特定债券信用评级 | 恒大信评-特定债券信用评级 | 3 | 3 | 2018-06-27 | 2018-07-01 | 2018-06-20 | 2018-06-28 | 1.4375 | 1 | 0.25 | 0.14815
万三 | 日志查询 | 日志查询 | 2 | 2 | 2018-04-11 | 2018-04-12 | 2018-04-09 | 2018-04-10 | 2 | 1 | 0.125 | 0.058824
万三 | 邮件配置功能迁移 | 邮件配置功能迁移 | 1 | 1 | 2018-05-09 | 2018-05-10 | 2018-05-10 | 2018-05-11 | 1
汪航 | 办公审批系统-权限申请模块需求变更 | 办公审批系统-权限申请模块需求变更 | 2 | 2 | 2018-06-15 | 2018-06-16 | 2018-06-15 | 2018-06-15 | 1 | 4 | 0.8125 | 0.44828
汪航 | “邮件知会”功能需求 | “邮件知会”功能需求 | 3 | 3 | 2018-06-22 | 2018-06-27 | 2018-06-21 | 2018-06-26 | 2.25 | 1 | 0.125 | 0.052632
汪荣 | 太平资产移动审批--新增因私出国（境）管理需求_20180315 | 太平资产移动审批--新增因私出国（境）管理需求_20180315 | 4 | 16 | 2018-04-08 | 2018-04-20 | 2018-04-09 | 2018-04-20 | 0.875 | 5 | 0.6875 | 0.44
汪荣 | 手机端同步流程处理页面 | 手机端同步流程处理页面 | 2.5 | 8 | 2018-04-10 | 2018-04-26 | 2018-04-09 | 2018-04-18 | 3.75 | 24 | 1.8125 | 0.32584
汪荣 | APP-股票入库 | APP-股票入库 | 1.5 | 3 | 2018-04-13 | 2018-04-20 | 2018-04-16 | 2018-04-20 | 1.5 | 3 | 0.3125 | 0.17241
汪荣 | 手机端漏洞扫描 | 手机端漏洞扫描 | 2 | 5 | 2018-04-20 | 2018-04-23 | 2018-04-19 | 2018-04-26 | 1.6875
汪荣 | 手机端同步流程处理页面-20180507 | 手机端同步流程处理页面 | 1.5 | 3.5 | 2018-04-20 | 2018-05-01 | 2018-05-07 | 2018-05-08 | 0.875 | 24 | 1.8125 | 0.67442
汪荣 | 手机端ipo分配人页面修改流程调整 | 手机端ipo分配人页面修改流程调整 | 2 | 4.5 | 2018-04-23 | 2018-04-24 | 2018-04-23 | 2018-04-24 | 0.65625
汪荣 | 手机端报告查询和出差流程审批页面详情展示处理 | 手机端报告查询和出差流程审批页面详情展示处理 | 1 | 4 | 2018-04-25 | 2018-05-13 | 2018-04-25 | 2018-05-14 | 1.0312 | 3 | 0.3125 | 0.23256
汪荣 | 手机漏洞扫描后台支持 | 手机漏洞扫描后台支持 | 1 | 6 | 2018-04-30 | 2018-04-30 | 2018-04-28 | 2018-04-28 | 0.875
汪荣 | 太平资产移动审批--普通债(一级市场投标)需求变更_20180502 | 太平资产移动审批--普通债(一级市场投标)需求变更_20180502 | 2 | 9 | 2018-05-03 | 2018-05-16 | 2018-05-04 | 2018-05-16 | 1.625 | 3 | 0.5 | 0.23529
汪荣 | 手机端审批页面增加低级错误统计 | 手机端审批页面增加低级错误统计 | 1.5 | 3 | 2018-05-08 | 2018-05-09 | 2018-05-08 | 2018-05-10 | 1.3438
汪荣 | 太平资产移动审批--因私出国需求变更_20180507 | 太平资产移动审批--因私出国需求变更_20180507 | 2 | 6 | 2018-05-09 | 2018-05-16 | 2018-05-10 | 2018-05-14 | 0.53125 | 7 | 1.525 | 0.74164
汪荣 | App查询报告时间修改 | App查询报告时间修改 | 1 | 2 | 2018-05-11 | 2018-05-14 | 2018-05-11 | 2018-05-16 | 1 | 2 | 0.1875 | 0.15789
汪荣 | 去掉app通讯录 | 去掉app通讯录 | 1 | 2 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 2018-05-30 | 0.375
汪荣 | 手机合规提交 | 手机合规提交 | 3 | 6 | 2018-06-05 | 2018-06-07 | 2018-06-05 | 2018-06-12 | 2.875 | 6 | 1.25 | 0.30303
汪荣 | 20180605_太平资产移动审批_债券一级市场需求变更（移动端调整） | 20180605_太平资产移动审批_债券一级市场需求变更 | 1 | 3 | 2018-06-12 | 2018-06-17 | 2018-06-11 | 2018-06-12 | 1 | 10 | 1.0625 | 0.51515
汪荣 | 离职流程（ipad） | 离职流程（ipad） | 3 | 3 | 2018-06-21 | 2018-06-29 | 2018-06-21 | 2018-06-25 | 2.375 | 1
王风旺 | 会议管理新增字段-会议标题 | 会议管理新增字段-会议标题 | 1 | 1 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 0.375
王风旺 | 13全景图利率展示优化需求分析 | 13全景图利率展示优化需求分析 |  | 2 | 2018-04-16 | 2018-04-20 | 2018-04-23 | 2018-04-24 | 0.8125 | 13 | 1.325 | 0.61988
王风旺 | 股权投资-评审合规发起材料补充需求 | 股权投资-评审合规发起材料补充需求 | 1 | 1 | 2018-04-19 | 2018-04-19 | 2018-04-19 | 2018-04-25 | 4.7625 | 9 | 2 | 0.29575
王风旺 | ios下载问题处理 | ios下载问题处理 | 1 | 2 | 2018-05-16 | 2018-05-16 | 2018-05-15 | 2018-05-18 | 0
王风旺 | 移动端下载优化 | 移动端下载优化 | 1 | 1 | 2018-05-22 | 2018-05-22 | 2018-05-21 | 2018-05-22 | 1.1875
王风旺 | 发行端去掉上一阶段验证 | 发行端去掉上一阶段验证 | 0.1 | 0.1 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 0.25
王祥 | 卖方观点-券商选择 | 卖方观点-券商选择 |  | 3 | 2018-04-03 | 2018-04-13 | 2018-04-13 | 2018-04-16 | 2 | 63 | 8.4 | 0.80769
王祥 | 卖方观点-券商荐股 | 卖方观点-券商荐股 | 10 | 20 | 2018-04-03 | 2018-04-20 | 2018-04-03 | 2018-05-07 | 10.125 | 30 | 4.475 | 0.30651
王祥 | 卖方观点-我的订阅 | 卖方观点-我的订阅 | 3 | 5 | 2018-04-03 | 2018-04-13 | 2018-04-10 | 2018-04-24 | 2.8125 | 6 | 0.675 | 0.19355
王祥 | 日常工作-路演、活动 | 日常工作-路演、活动 | 10 | 20 | 2018-04-09 | 2018-04-22 | 2018-03-26 | 2018-04-24 | 5.1875 | 12 | 1.9375 | 0.27193
王祥 | 日常工作-路演、活动-变更 | 日常工作-路演、活动 | 2 | 8 | 2018-05-07 | 2018-05-11 | 2018-05-07 | 2018-05-08 |  | 12 | 1.9375
王祥 | 华泰柏瑞新增禁投库流程 | 华泰柏瑞新增禁投库流程 | 1 | 1 | 2018-05-29 | 2018-05-31 | 2018-05-29 | 2018-05-29 | 1.0125 | 4 | 0.4375 | 0.30172
王祥 | 新股上市未入库提醒 | 新股上市未入库提醒 | 2 | 2 | 2018-06-04 | 2018-06-07 | 2018-06-06 | 2018-06-07 | 2 | 1 | 0.1875 | 0.085714
王祥 | 大成基金-重点持仓股票跟踪 | 大成基金-重点持仓股票跟踪 | 3 | 3 | 2018-06-08 | 2018-06-12 | 2018-06-11 | 2018-06-14 | 1.6125 | 7 | 1.1875 | 0.42411
王祥 | 大成基金-核心库补报告 | 大成基金-核心库补报告 | 3 | 3 | 2018-06-13 | 2018-06-19 | 2018-06-12 | 2018-06-14 | 3 | 5 | 1.0625 | 0.26154
王祥 | 大成基金-临时代码投资池维护 | 大成基金-临时代码投资池维护 | 1 | 1 | 2018-06-20 | 2018-06-22 | 2018-06-15 | 2018-06-15 | 1
王祥 | 民生加银投资池新增需求 | 民生加银投资池新增需求 | 7 | 7 | 2018-06-20 | 2018-06-26 | 2018-06-19 | 2018-06-22 | 3.25 | 5 | 0.8125 | 0.2
吴攀 | 银河基金sirm债券临时代码导入需求 | 银河基金sirm债券临时代码导入需求 | 4 | 4 | 2018-03-30 | 2018-04-03 | 2018-03-29 | 2018-04-02 | 3.1875 | 5 | 0.4375 | 0.12069
吴攀 | 中融基金投资池新增需求20180330 | 中融基金投资池新增需求20180330 | 3 | 8 | 2018-04-02 | 2018-04-13 | 2018-04-02 | 2018-04-12 | 1.875 | 11 | 0.8375 | 0.30876
吴攀 | 银河基金sirm新增支持恒生o32格式的excel导出 | 银河基金sirm新增支持恒生o32格式的excel导出 | 3 | 3 | 2018-04-09 | 2018-04-12 | 2018-04-09 | 2018-04-12 | 1.9375 | 4 | 0.625 | 0.2439
吴攀 | 投资池流程撤销需求 | 投资池流程撤销需求 | 2 | 2 | 2018-04-09 | 2018-04-19 | 2018-04-08 | 2018-04-09 | 1.375 | 1 | 0.1375 | 0.090909
吴攀 | 中海投资池调整发起后页面增加展示流程步骤 | 中海投资池调整发起后页面增加展示流程步骤 | 1 | 1 | 2018-04-16 | 2018-04-18 | 2018-04-13 | 2018-04-16 | 0.75
吴攀 | 华泰柏瑞股票入池超期提醒-20180423 | 华泰柏瑞股票入池超期提醒 | 2 | 2 | 2018-04-25 | 2018-04-28 | 2018-04-25 | 2018-04-26 | 1.4375 | 5 | 0.5 | 0.25806
吴攀 | 浦银禁投白名单-20180426(转移) | 浦银禁投白名单(转移) | 2 | 2 | 2018-04-27 | 2018-05-11 | 2018-04-26 | 2018-04-27 | 1.1875 | 6 | 0.6875 | 0.36667
吴攀 | 债券池优化功能 | 债券池优化功能 | 6 | 6 | 2018-05-03 | 2018-05-11 | 2018-05-04 | 2018-05-08 | 2.375 | 5 | 0.8125 | 0.2549
吴攀 | 基金池需求 | 基金池需求 | 3 | 3 | 2018-05-03 | 2018-05-08 | 2018-05-03 | 2018-05-09 | 1 | 3 | 0.5625 | 0.36
吴攀 | 银河基金sirm新增支持恒生o32格式的excel导出-20180504 | 银河基金sirm新增支持恒生o32格式的excel导出 | 1 | 1 | 2018-05-04 | 2018-05-07 | 2018-05-04 | 2018-05-04 | 0.5 | 4 | 0.625 | 0.55556
吴攀 | 债基池债券池需求 | 债基池债券池需求 | 10 | 10 | 2018-05-09 | 2018-05-25 | 2018-05-09 | 2018-05-25 | 5.75 | 8 | 1.8125 | 0.23967
吴攀 | 调池客户使用修改需求文档 | 调池客户使用修改需求文档 | 1 | 1 | 2018-05-10 | 2018-05-11 | 2018-05-09 | 2018-05-09 | 0.3125 | 1 | 0.3125 | 0.5
吴攀 | 华泰柏瑞股票入池超期提醒-20180510 | 华泰柏瑞股票入池超期提醒 | 2 | 2 | 2018-05-15 | 2018-05-17 | 2018-05-15 | 2018-05-16 | 0.9375 | 5 | 0.5 | 0.34783
吴攀 | 中海Excel导入增加提交确认页面 | 中海Excel导入增加提交确认页面 | 2 | 2 | 2018-05-21 | 2018-05-22 | 2018-05-21 | 2018-05-22 | 1.125 | 1 | 0.125 | 0.1
吴攀 | 国寿安保投资池新增需求 | 国寿安保投资池新增需求 | 2 | 2 | 2018-05-23 | 2018-05-24 | 2018-05-22 | 2018-05-24 | 1.5 | 2 | 0.25 | 0.14286
吴攀 | 港股股票池定制 | 港股股票池定制 | 2 | 2 | 2018-05-29 | 2018-05-30 | 2018-05-28 | 2018-05-29 | 1.1875 | 1 | 0.125 | 0.095238
吴攀 | 华泰柏瑞报告超期提醒变更 | 华泰柏瑞报告超期提醒变更 | 2 | 2 | 2018-05-30 | 2018-05-31 | 2018-05-29 | 2018-05-30 | 1.1875 | 2 | 0.25 | 0.17391
吴攀 | 信评评级功能使用时，如有调池操作，需要触发联动和互斥关系 | 信评评级功能使用时，如有调池操作，需要触发联动和互斥关系 | 2 | 2 | 2018-06-01 | 2018-06-04 | 2018-06-01 | 2018-06-02 | 1.375 | 1 | 0.125 | 0.083333
吴攀 | 大成基金-建立专户股票基金备选库 | 大成基金-建立专户股票基金备选库 | 3 | 3 | 2018-06-06 | 2018-06-08 | 2018-06-04 | 2018-06-06 | 2.375 | 8 | 1.75 | 0.42424
吴攀 | 中海调池结果提醒内容调整V1.1 | 中海调池结果提醒内容调整 | 1 | 1 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 0.3125 | 4 | 1 | 0.7619
吴攀 | 中海调池结果提醒内容调整 | 中海调池结果提醒内容调整 | 1 | 1 | 2018-06-12 | 2018-06-12 | 2018-06-11 | 2018-06-12 | 0.5625 | 4 | 1 | 0.64
吴攀 | 大成基金-债券池到期自动出池 | 大成基金-债券池到期自动出池 | 1 | 1 | 2018-06-14 | 2018-06-18 | 2018-06-06 | 2018-06-07 | 0.75 | 1 | 0.1875 | 0.2
吴攀 | 基金excel导入添加导出O32格式的投资池列表 | 基金excel导入添加导出O32格式的投资池列表 | 2 | 2 | 2018-06-20 | 2018-06-21 | 2018-06-20 | 2018-06-21 | 0.375 | 1 | 0.0625 | 0.14286
吴攀 | 债基池债券池需求2 | 债基池债券池需求 | 1 | 1 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 0.3125 | 8 | 1.8125 | 0.85294
向岚 | 6.1统计分析-动态统计报表-1 | 6.1统计分析-动态统计报表 |  | 5 | 2018-04-11 | 2018-04-15 | 2018-04-11 | 2018-04-11 | 1.5 | 10 | 0.4375 | 0.22581
向岚 | 2.9募集发行-放款管理-1 | 2.9募集发行-放款管理 | 5 | 5 | 2018-04-11 | 2018-04-20 | 2018-04-12 | 2018-04-11 | 0.5 | 11 | 0.6375 | 0.56044
向岚 | 托管户划款需求 | 托管户划款需求 |  | 5 | 2018-05-10 | 2018-05-13 | 2018-05-10 | 2018-05-16 | 1.4375 | 8 | 3.25 | 0.69333
向岚 | 清算报告生成 | 清算报告生成 |  | 2 | 2018-05-16 | 2018-05-18 | 2018-05-18 | 2018-05-18 | 1.625 | 2 | 0.125 | 0.071429
向岚 | 项目评级 | 项目评级 | 10 | 10 | 2018-05-30 | 2018-06-12 | 2018-05-30 | 2018-06-11 | 5.375 | 21 | 2.5625 | 0.32283
肖楚 | 2.1版本需求优化1 | 2.1版本需求优化1 | 2 | 2 | 2018-04-10 | 2018-04-13 | 2018-04-11 | 2018-04-17 | 2 | 2 | 0.6875 | 0.25581
肖楚 | 新发债评级不更新主体内评与内部展望(转移) | 新发债评级不更新主体内评与内部展望(转移) | 1 | 1 | 2018-04-16 | 2018-04-18 | 2018-04-17 | 2018-04-17 | 0.625 | 1 | 0.375 | 0.375
肖楚 | 汇添富2018年4月债券选择控件优化需求 | 汇添富2018年4月债券选择控件优化需求 | 1 | 1 | 2018-04-18 | 2018-04-20 | 2018-04-19 | 2018-04-19 | 0.25
肖楚 | 中观高频季节性数据图表(转移) | 中观高频季节性数据图表(转移) | 3 | 3 | 2018-04-20 | 2018-04-27 | 2018-04-19 | 2018-04-27 | 2.975 | 2 | 0.5 | 0.14388
肖楚 | 市场观点修改20180419(转移) | 市场观点修改20180419(转移) | 1 | 1 | 2018-04-20 | 2018-04-26 | 2018-04-19 | 2018-04-19 | 0.375
肖楚 | 可转债一键入库修改(转移) | 可转债一键入库修改(转移) | 3 | 3 | 2018-04-25 | 2018-05-04 | 2018-04-27 | 2018-05-04 | 3 | 3 | 0.0875 | 0.02834
肖楚 | 负面新闻增加重点关注 | 负面新闻增加重点关注 | 2 | 2 | 2018-05-08 | 2018-05-10 | 2018-05-08 | 2018-05-09 | 2 | 3 | 0.3125 | 0.13514
肖楚 | 存量债新增需求(转移) | 存量债新增需求(转移) | 3 | 3 | 2018-05-11 | 2018-05-17 | 2018-05-14 | 2018-05-16 | 2.9375
肖楚 | 舆情信息增加持仓消息提醒(转移) | 舆情信息增加持仓消息提醒(转移) | 2 | 2 | 2018-05-11 | 2018-05-17 | 2018-05-14 | 2018-05-17 | 2
肖丹 | 客户关系公共邮箱维护 | 客户关系公共邮箱维护 | 3 | 3 | 2018-03-28 | 2018-04-04 | 2018-03-28 | 2018-03-28 | 1.25 | 2 | 0.25 | 0.16667
肖丹 | 路演预约日程安排展示需求 | 路演预约日程安排展示需求 | 3 | 3 | 2018-04-03 | 2018-04-11 | 2018-04-03 | 2018-04-16 | 1.3625
肖丹 | 估值模型升级（历史报告评级和目标价保留及合规更新） | 估值模型升级（历史报告评级和目标价保留及合规更新） | 1 | 2 | 2018-04-12 | 2018-04-16 | 2018-04-13 | 2018-04-16 | 1 | 7 | 1.375 | 0.57895
肖丹 | 关键报告需求变更 | 关键报告需求变更 | 1 | 1 | 2018-04-18 | 2018-05-13 | 2018-04-18 | 2018-04-18 | 1 | 3 | 0.125 | 0.11111
肖丹 | 中泰证券-媒体活动修改20180410 | 中泰证券-媒体活动修改20180410 |  | 1 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-26 | 1.125
肖丹 | 排查SimpleDateFormat或者DecimalFormat | 排查SimpleDateFormat或者DecimalFormat | 3 | 3 | 2018-04-25 | 2018-05-30 | 2018-05-11 | 2018-05-11 | 1.75
肖丹 | 排查SimpleDateFormat或者DecimalFormat | 排查SimpleDateFormat或者DecimalFormat | 3 | 3 | 2018-04-25 | 2018-05-30 | 2018-05-08 | 2018-05-14 | 1.5
肖丹 | 排查SimpleDateFormat或者DecimalFormat | 排查SimpleDateFormat或者DecimalFormat | 3 | 3 | 2018-04-25 | 2018-05-30 | 2018-05-07 | 2018-05-08 | 1.5
肖丹 | 手机端报告查询和出差流程审批页面详情展示处理 | 手机端报告查询和出差流程审批页面详情展示处理 | 2 | 4 | 2018-04-25 | 2018-05-13 | 2018-04-25 | 2018-05-14 | 2 | 3 | 0.3125 | 0.13514
肖丹 | 关联报告优化 | 关联报告优化 | 1 | 1 | 2018-04-26 | 2018-05-06 | 2018-05-03 | 2018-05-03 | 1
肖丹 | 估值模型升级需求变更-模板修改 | 估值模型升级 | 0.2 | 3.2 | 2018-04-27 | 2018-05-06 | 2018-04-28 | 2018-05-03 | 0.25 | 6 | 0.1375 | 0.35484
肖丹 | 内部报告App接口，客户查询禁止复制客户相关信息 | 内部报告App接口，客户查询禁止复制客户相关信息 | 3 | 3 | 2018-05-17 | 2018-05-18 | 2018-05-18 | 2018-05-22 | 1.625 | 1 | 0.0625 | 0.037037
肖丹 | 语义分析、债券识别 | 语义分析、债券识别 | 5 | 5 | 2018-05-18 | 2018-05-25 | 2018-05-18 | 2018-05-22 | 2.125
肖丹 | 上市公司交流会需求第1部分 | 上市公司交流会需求第1部分 | 3 | 3 | 2018-05-25 | 2018-05-29 | 2018-05-28 | 2018-06-15 | 2.75 | 7 | 0.4125 | 0.13043
肖丹 | 上市公司交流会需求第2部分 | 上市公司交流会需求第2部分 | 5 | 5 | 2018-05-30 | 2018-06-05 | 2018-05-30 | 2018-06-19 | 5
肖丹 | 关键报告需求变更2 | 关键报告需求变更 | 1 | 1 | 2018-06-14 | 2018-06-20 | 2018-06-15 | 2018-06-21 | 0.875 | 3 | 0.125 | 0.125
肖丹 | 出差调研报告撰写提醒 | 出差调研报告撰写提醒 | 1 | 1 | 2018-06-22 | 2018-06-26 | 2018-06-26 | 2018-06-26 | 1 | 1 | 0.125 | 0.11111
肖晶 | 前海联合券商打分修改 | 前海联合券商打分修改 | 0.5 | 5 | 2018-03-22 | 2018-04-06 | 2018-03-23 | 2018-04-08 | 0.0625 | 11 | 0.55 | 0.89796
肖晶 | 国元证券绩效考核20180207-20180325 | 国元证券绩效考核20180207 | 1 | 3 | 2018-03-26 | 2018-04-06 | 2018-03-25 | 2018-04-08 | 1.9375 | 31 | 3.4875 | 0.64286
肖晶 | 批量报告入库流程发起审批 | 批量报告入库流程发起审批 | 1 | 1 | 2018-04-03 | 2018-05-02 | 2018-04-02 | 2018-04-04 | 0.9375 | 3 | 0.25 | 0.21053
肖晶 | 东方证投km出差申请发送短信逻辑修改 | 东方证投km出差申请发送短信逻辑修改 | 1 | 1 | 2018-04-03 | 2018-04-03 | 2018-04-02 | 2018-04-02 | 0.1875 | 2 | 0.1875 | 0.5
肖晶 | 客户oracle10g数据库更换为oracle12c测试-20180418 | 客户oracle10g数据库更换为oracle12c测试 | 2 | 2 | 2018-04-19 | 2018-04-20 | 2018-04-19 | 2018-04-20 | 1 | 13 | 1.325 | 0.56989
肖晶 | wind数据源切换为oracle12c版本需求 | wind数据源切换为oracle12c版本需求 | 2 | 3 | 2018-04-24 | 2018-04-30 | 2018-04-19 | 2018-05-25 | 6.5 | 5 | 0.8125 | 0.11111
肖晶 | 绩效统计菜单下券商打分下的公司年度总分，查看页面添加序列显示 | 绩效统计菜单下券商打分下的公司年度总分，查看页面添加序列显示 | 0.2 | 0.2 | 2018-06-11 | 2018-06-11 | 2018-06-08 | 2018-06-08 | 0.125
肖晶 | 批量上传内部报告 | 批量上传内部报告 | 1 | 1 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | 0.5 | 1 | 0.25 | 0.33333
肖晶 | 批量上传内部报告变更 | 批量上传内部报告 | 0.2 | 0.2 | 2018-06-14 | 2018-06-14 | 2018-06-13 | 2018-06-13 | 0.25 | 1 | 0.25 | 0.5
肖晶 | 派点打分功能修改_20180417 | 派点打分功能修改_20180417 | 3 | 3 |  |  | 2018-04-18 | 2018-04-20 | 1.2875 | 1 | 0.0625 | 0.046296
熊兵 | 活动预约研究员默认参与打分 | 活动预约研究员默认参与打分 | 1 | 1 | 2018-04-02 | 2018-04-08 | 2018-04-03 | 2018-04-03 | 0.375
熊兵 | 投研交互券商活动功能优化_20180410 | 投研交互券商活动功能优化_20180410 | 1.5 | 1.5 | 2018-04-09 | 2018-04-12 | 2018-04-10 | 2018-04-10 | 0.875
熊兵 | 调研、公告点评变更 | 调研、公告点评 | 2 | 2 | 2018-04-09 | 2018-04-11 | 2018-04-09 | 2018-04-09 | 0.8125 | 2 | 0.0125 | 0.015152
熊兵 | 建信基金系统用户拆分（接口开发） | 建信基金系统用户拆分（接口开发） | 5 | 5 | 2018-04-10 | 2018-04-17 | 2018-04-09 | 2018-04-18 | 5.6125 | 10 | 1.3875 | 0.19821
熊兵 | 券商取消活动和角色联动展示 | 券商取消活动和角色联动展示 | 4 | 4 | 2018-04-23 | 2018-04-27 | 2018-04-24 | 2018-04-28 | 5.3125 | 6 | 0.275 | 0.049217
熊兵 | 券商活动操作日志记录 | 券商活动操作日志记录 | 1 | 1 | 2018-04-28 | 2018-05-04 | 2018-05-02 | 2018-05-03 | 2.375
熊兵 | 账号离职和用户同步记录查看 | 账号离职和用户同步记录查看 | 6 | 9 | 2018-05-03 | 2018-05-18 | 2018-05-03 | 2018-05-22 | 10.1375 | 6 | 0.575 | 0.053676
熊兵 | 后台打印券商通讯录操作日志 | 后台打印券商通讯录操作日志 | 3 | 3 | 2018-05-23 | 2018-05-25 | 2018-05-23 | 2018-05-25 | 2.625 | 1 | 0.0625 | 0.023256
熊兵 | 投研交互增加页面维护活动类型 | 投研交互增加页面维护活动类型 | 5 | 5 | 2018-05-28 | 2018-06-01 | 2018-05-28 | 2018-05-28 | 0.75 | 2 | 0.125 | 0.14286
熊兵 | 0528路演类型提出来成两个菜单 | 0528路演类型提出来成两个菜单 | 2 | 2 | 2018-05-29 | 2018-05-30 | 2018-05-29 | 2018-05-29 | 1.1875
熊兵 | 投研交互打分控件修改 | 投研交互打分控件修改 | 2 | 2 | 2018-05-31 | 2018-06-01 | 2018-05-29 | 2018-05-30 | 0.9375 | 4 | 0.05 | 0.050633
熊兵 | irex消息发送问题处理 | irex消息发送问题处理 |  | 5 | 2018-06-04 | 2018-06-08 | 2018-06-01 | 2018-06-08 | 6.0375 | 1
熊兵 | 投研交互app我的事宜增加打分模块 | 投研交互app我的事宜增加打分模块 | 5 | 5 | 2018-06-11 | 2018-06-15 | 2018-06-11 | 2018-06-13 | 2.975 | 4 | 0.625 | 0.17361
徐红英 | 内部报告迁移 | 内部报告迁移 | 3 | 3 | 2018-04-02 | 2018-04-08 | 2018-03-30 | 2018-04-08 | 3.35 | 6 | 0.1125 | 0.032491
徐红英 | 报告模板更新 | 报告模板更新 | 1 | 6 | 2018-04-10 | 2018-04-13 | 2018-04-10 | 2018-04-11 | 0.75 | 8 | 0.75 | 0.5
徐红英 | 东方投研债券报告模板及报告提交解析解析 | 东方投研债券报告模板及报告提交解析解析 | 4 | 7 | 2018-04-16 | 2018-04-24 | 2018-04-16 | 2018-04-19 | 3.9863 | 6 | 0.7875 | 0.16496
徐红英 | 中银国际销售需求-报告插件0419 | 中银国际销售需求-报告插件0419 | 3 | 4 | 2018-04-20 | 2018-04-26 | 2018-04-20 | 2018-04-26 | 2.825 | 25 | 1.35 | 0.32335
徐红英 | 信评内部报告修改需求-20180425 | 信评内部报告修改需求 | 1 | 2 | 2018-04-25 | 2018-05-02 | 2018-04-25 | 2018-05-02 | 0.95625 | 11 | 0.4625 | 0.32599
徐红英 | 报告插件更改 | 报告插件更改 | 2 | 2 | 2018-04-26 | 2018-04-27 | 2018-04-23 | 2018-04-27 | 1.875 | 16 | 0.8125 | 0.30233
徐红英 | 估值模型升级需求变更-模板修改 | 估值模型升级 | 3 | 3.2 | 2018-04-27 | 2018-05-06 | 2018-04-28 | 2018-05-03 | 3.1187 | 6 | 0.1375 | 0.042226
徐红英 | 报告模板更新-20180502 | 报告模板更新 | 0.5 | 0.5 | 2018-05-02 | 2018-05-02 | 2018-05-02 | 2018-05-02 | 0.5 | 8 | 0.75 | 0.6
徐红英 | 固收报告新增定性评价表格 | 固收报告新增定性评价表格 |  | 2 | 2018-05-02 | 2018-05-04 | 2018-05-03 | 2018-05-04 | 0.9625
徐红英 | 中银国际销售需求-报告插件0419补充 | 中银国际销售需求-报告插件0419补充 | 0.5 | 0.5 | 2018-05-04 | 2018-05-08 | 2018-05-04 | 2018-05-07 | 0.475 | 2 | 0.03875 | 0.075426
徐红英 | 信评内部报告修改需求-20180508 | 信评内部报告修改需求 | 0.5 | 1 | 2018-05-09 | 2018-05-10 | 2018-05-08 | 2018-05-08 | 0.5 | 11 | 0.4625 | 0.48052
徐红英 | 广发-报告模版开发 | 广发-报告模版开发 | 5 | 7 | 2018-05-14 | 2018-05-22 | 2018-05-14 | 2018-05-22 | 5.7625 | 20 | 2.2 | 0.2763
徐红英 | excel插件更新-20180521 | excel插件更新 | 2 | 2 | 2018-05-22 | 2018-05-25 | 2018-05-22 | 2018-05-24 | 1.95 | 4 | 0.25 | 0.11364
徐红英 | 广发-英文报告模板开发和解析-尾页声明变更 | 广发-英文报告模板开发和解析 | 6 | 10 | 2018-05-24 | 2018-06-05 | 2018-05-24 | 2018-05-31 | 5.0625 | 22 | 1.25 | 0.19802
徐红英 | 报告模板需求开发-尾页更新 | 报告模板需求开发 | 3 | 3 | 2018-05-25 | 2018-05-30 | 2018-05-31 | 2018-05-31 | 0.0125 | 49 | 10.8875 | 0.99885
徐红英 | 报告插件选择作者需求变更 | 报告插件选择作者需求变更 | 1 | 2 | 2018-06-04 | 2018-06-04 | 2018-06-03 | 2018-06-04 | 0.8375 | 4 | 0.875 | 0.51095
徐红英 | 新增模板 | 新增模板 | 2.5 | 3.5 | 2018-06-06 | 2018-06-07 | 2018-06-05 | 2018-06-07 | 2.3625 | 8 | 0.75 | 0.24096
徐红英 | 估值模型导入及报告模板画图插件测试 | 估值模型导入及报告模板画图插件测试 | 2 | 2 | 2018-06-08 | 2018-06-12 | 2018-06-07 | 2018-06-11 | 1.125 | 12 | 0.275 | 0.19643
徐红英 | 广发-报告插件格式刷 | 广发-报告插件格式刷 | 4 | 5 | 2018-06-13 | 2018-06-21 | 2018-06-12 | 2018-06-20 | 3.7375 | 4 | 0.05 | 0.013201
徐红英 | 系统报告功能修改 | 系统报告功能修改 | 1.5 | 3 | 2018-06-14 | 2018-06-20 | 2018-06-13 | 2018-06-19 |  | 3 | 0.5625
徐欢 | 机构和模板关联 | 机构和模板关联 | 2 | 2 | 2018-04-05 | 2018-04-10 | 2018-04-07 | 2018-04-07 | 2
徐欢 | 业务日志 | 业务日志 | 1 | 1 | 2018-05-16 | 2018-05-18 | 2018-05-18 | 2018-05-22 | 1.875 | 2 | 1.0625 | 0.3617
徐俊 | 5基础信息 | 5基础信息 |  | 20 | 2018-02-28 | 2018-04-14 | 2018-02-27 | 2018-03-01 | 1.875
徐俊 | 4.2风险管理-风险分级 | 4.2风险管理-风险分级 |  | 20 | 2018-02-28 | 2018-04-09 | 2018-03-21 | 2018-04-02 | 5.4375
徐俊 | 存续期现场调查 | 存续期现场调查 |  | 2 | 2018-05-16 | 2018-05-18 | 2018-05-18 | 2018-05-21 | 2.5 | 5 | 1.75 | 0.41176
徐俊 | 缴款管理 | 缴款管理 |  | 1 | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-24 | 1 | 1 | 0.125 | 0.11111
徐俊 | 财务数据模板调整 | 财务数据模板调整 |  | 3 | 2018-06-11 | 2018-06-12 | 2018-06-13 | 2018-06-12 | 1 | 2 | 0.5 | 0.33333
徐俊 | 数据权限 | 数据权限 | 2 | 2 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | 1.375 | 2 | 0.25 | 0.15385
徐俊 | 资料移交优化 | 资料移交优化 |  | 2 | 2018-06-26 | 2018-06-26 | 2018-06-25 | 2018-06-25 | 0.125
徐立 | v3.0-需求工作单审批流程优化20180131-20180416 | v3.0-需求工作单审批流程优化20180131 | 0.5 | 1 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-18 | 0.25 | 6 | 1.15 | 0.82143
徐立 | BUG管理优化20171027-20180420 | BUG管理优化20171027 | 0.1 | 0.1 | 2018-04-20 | 2018-04-20 | 2018-04-23 | 2018-04-23 | 0.375 | 25 | 5.5375 | 0.93658
徐立 | v3.1-测试任务查询优化20180423 | v3.1-测试任务查询优化20180423 | 0.5 | 0.5 | 2018-04-23 | 2018-04-24 | 2018-04-23 | 2018-04-23 | 0.625 | 6 | 2.0625 | 0.76744
徐立 | v3.1-立项审批流程优化20180425 | v3.1-立项审批流程优化20180425 | 0.5 | 1 | 2018-04-26 | 2018-05-04 | 2018-05-04 | 2018-05-07 | 0.875 | 14 | 1.85 | 0.6789
徐立 | v3.1-需求工作单优化20180425-20180510 | v3.1-需求工作单优化20180425 | 0.5 | 0.5 | 2018-05-10 | 2018-05-11 | 2018-05-10 | 2018-05-11 | 1.25 | 10 | 2.3375 | 0.65157
徐立 | v3.1-工时统计优化 | v3.1-工时统计优化 | 2 | 3 | 2018-05-22 | 2018-05-25 | 2018-05-21 | 2018-05-23 | 2.9375 | 10 | 2.1625 | 0.42402
徐立 | v3.1-需求重新开发优化 | v3.1-需求重新开发优化 | 1 | 1.5 | 2018-05-28 | 2018-06-01 | 2018-05-28 | 2018-06-04 | 1.5
徐立 | v3.1-成本评估优化20180604 | v3.1-成本评估优化20180604 | 0.5 | 1 | 2018-06-04 | 2018-06-05 | 2018-06-04 | 2018-06-05 | 1.025
徐立 | v3.2-BUG管理优化20180426 | v3.2-BUG管理优化20180426 | 6.5 | 7 | 2018-06-06 | 2018-06-15 | 2018-06-07 | 2018-06-21 | 9.375 | 9 | 1.3875 | 0.12892
许云兰 | 一对一资金追加提取变更 | 一对一资金追加提取变更 | 0.5 | 0.5 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 0.25 | 1 | 0.1875 | 0.42857
许云兰 | 风险提醒 | 风险提醒 | 2 | 2 | 2018-04-02 | 2018-04-02 | 2018-03-30 | 2018-03-30 | 1.875 | 9 | 0.4 | 0.17582
许云兰 | 关联流程 | 关联流程 | 1 | 2 | 2018-04-02 | 2018-04-04 | 2018-04-04 | 2018-04-11 | 0.9125 | 6 | 1.0625 | 0.53797
许云兰 | 产品文档上传 | 产品文档上传 | 3 | 3 | 2018-04-02 | 2018-04-08 | 2018-04-02 | 2018-04-08 | 3.125 | 3 | 0.25 | 0.074074
许云兰 | 加签页面替换或补充附件 | 加签页面替换或补充附件 | 6 | 6 | 2018-04-11 | 2018-04-20 | 2018-04-11 | 2018-04-20 | 5.6875
许云兰 | 法律文件变更用印流程变更 | 法律文件变更用印流程变更 | 1 | 1 | 2018-04-12 | 2018-04-12 | 2018-04-11 | 2018-04-11 | 0.9375 | 2 | 0.25 | 0.21053
许云兰 | 公募产品要素、权限更改 | 公募产品要素、权限更改 | 5 | 5 | 2018-04-24 | 2018-05-03 | 2018-04-23 | 2018-05-08 | 7.625 | 4 | 0.275 | 0.03481
许云兰 | 公募产品新增份额 | 公募产品新增份额 | 3 | 3 | 2018-05-08 | 2018-05-17 | 2018-05-07 | 2018-05-16 | 3.0375 | 1 | 0.5625 | 0.15625
许云兰 | 专户开放期管理权限更改 | 专户开放期管理权限更改 | 2 | 2 | 2018-05-08 | 2018-05-11 | 2018-05-09 | 2018-05-09 | 1
许云兰 | 留言功能修改 | 留言功能修改 | 2 | 2 | 2018-05-17 | 2018-05-18 | 2018-05-17 | 2018-05-18 | 1.875 | 2 | 0.0625 | 0.032258
许云兰 | 流程功能优化 | 流程功能优化 | 2 | 2 | 2018-06-14 | 2018-06-22 | 2018-06-13 | 2018-06-15 | 1.75 | 4 | 0.5 | 0.22222
许云兰 | oa接口任务 | oa接口任务 | 5 | 10 | 2018-06-22 | 2018-07-03 | 2018-06-21 | 2018-06-25 | 3.125 | 3 | 0.1875 | 0.056604
许琪 | 营改增需求 | 营改增需求 | 20 | 20 | 2018-03-14 | 2018-04-27 | 2018-03-13 | 2018-04-04 | 11.625 | 20 | 2.975 | 0.20377
许琪 | 划款指令批量打印 | 划款指令批量打印 | 10 | 10 | 2018-04-09 | 2018-04-30 | 2018-04-08 | 2018-04-11 | 3.375 | 3 | 0.5875 | 0.14826
许琪 | 投前功能调整 | 投前功能调整 | 4 | 4 | 2018-04-13 | 2018-04-18 | 2018-04-13 | 2018-04-19 | 5 | 2 | 0.125 | 0.02439
许琪 | 项目功能优化 | 项目功能优化 | 4 | 4 | 2018-04-23 | 2018-04-24 | 2018-04-20 | 2018-04-25 | 3.625 | 4 | 0.2125 | 0.055375
许琪 | 文件上传功能优化-到期产品放开测试 | 文件上传功能优化-到期产品放开测试 | 1 | 1 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-03 | 0.625 | 1 | 0.125 | 0.16667
严凯旋 | 资产处置 | 资产处置 | 1 | 1 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-01 | 0 | 1
严凯旋 | 项目跟踪 | 项目跟踪 | 1 | 1 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 0
严凯旋 | 项目分工 | 项目分工 | 1 | 1 | 2018-06-04 | 2018-06-04 | 2018-06-04 | 2018-06-01 | 0
严文旭 | 移动端接口开发 | 移动端接口开发 | 4 | 10 | 2018-04-10 | 2018-04-16 | 2018-04-10 | 2018-04-16 | 4.25 | 4 | 1.75 | 0.29167
杨凌薇 | 指标、参数修改需求 | 指标、参数修改需求 | 5 | 5 | 2018-04-26 | 2018-05-04 | 2018-04-26 | 2018-05-04 | 5.375 | 4 | 0.5625 | 0.094737
杨凌薇 | 模型配置 | 模型配置 | 2 | 11 | 2018-04-27 | 2018-05-11 | 2018-04-26 | 2018-05-11 |  | 28 | 2.975
杨凌薇 | 信评模型评级实例化，历史评级能够完美呈现(转移) | 信评模型评级实例化，历史评级能够完美呈现(转移) | 5 | 5 | 2018-05-18 | 2018-05-31 | 2018-05-28 | 2018-06-01 | 4.25 | 3 | 0.5 | 0.10526
杨凌薇 | 数据迁移联调 | 数据迁移联调 | 5 | 5 | 2018-05-21 | 2018-05-25 | 2018-05-22 | 2018-05-28 | 0.75 | 2 | 0.875 | 0.53846
杨凌薇 | 指标开发，中欧指标迁移(转移) | 指标开发，中欧指标迁移(转移) | 8 | 8 | 2018-06-07 | 2018-06-15 | 2018-06-07 | 2018-06-11 | 2.5 | 9 | 1.875 | 0.42857
杨凌薇 | 指标开发，中欧指标迁移(转移)-20180614 | 指标开发，中欧指标迁移(转移) | 1 | 1 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 2018-06-14 | 0 | 9 | 1.875 | 1
杨威 | 客户检测的超过1秒的sql优化 | 客户检测的超过1秒的sql优化 | 10 | 10 | 2018-04-24 | 2018-05-15 | 2018-04-24 | 2018-05-10 | 12.5
杨宇航 | 枚举管理功能迁移 | 枚举管理功能迁移 | 2 | 2 | 2018-04-12 | 2018-04-13 | 2018-04-12 | 2018-04-17 | 4 | 13 | 1 | 0.2
杨宇航 | 权限控制 | 权限控制 | 8 | 8 | 2018-04-20 | 2018-04-30 | 2018-04-20 | 2018-04-27 | 6 | 8 | 0.5 | 0.076923
杨宇航 | 活动作业监控功能迁移 | 活动作业监控功能迁移 | 2 | 2 | 2018-05-24 | 2018-06-01 | 2018-05-24 | 2018-05-25 | 1.625 | 6 | 0.875 | 0.35
杨宇航 | 日志查询增加导出功能 | 日志查询增加导出功能 | 1.5 | 1.5 | 2018-05-28 | 2018-05-29 | 2018-05-29 | 2018-05-28 | 1
杨宇航 | WEB报表管理5.0功能和我的WEB报表5.0功能迁移完善 | WEB报表管理5.0功能和我的WEB报表5.0功能迁移完善 | 6 | 6 | 2018-05-30 | 2018-06-06 | 2018-05-30 | 2018-06-05 | 4.75 | 2 | 0.25 | 0.05
杨宇航 | 监控邮件配置功能迁移 | 监控邮件配置功能迁移 | 2 | 2 | 2018-06-07 | 2018-06-08 | 2018-06-05 | 2018-06-07 | 2
杨宇航 | 数据质量--数据库配置 | 数据质量--数据库配置 | 1.5 | 1.5 | 2018-06-28 | 2018-06-29 | 2018-06-29 | 2018-06-29 | 2 | 3 | 0 | 0
杨婧 | 研究服务申请增加手机端功能 | 研究服务申请增加手机端功能 | 3 | 7 | 2018-03-30 | 2018-04-04 | 2018-03-30 | 2018-04-10 | 3.375 | 16 | 0.3875 | 0.10299
杨婧 | 进门财经审核增加手机展示 | 进门财经审核增加手机展示 | 3 | 7 | 2018-04-04 | 2018-04-15 | 2018-04-03 | 2018-04-12 | 3.625
杨婧 | 太平资产移动审批--新增因私出国（境）管理需求_20180315 | 太平资产移动审批--新增因私出国（境）管理需求_20180315 |  | 16 | 2018-04-08 | 2018-04-20 | 2018-04-09 | 2018-04-20 | 1.625 | 5 | 0.6875 | 0.2973
杨婧 | 进门财经审核手机端合规展示 | 进门财经审核手机端合规展示 | 1 | 2 | 2018-04-13 | 2018-04-20 | 2018-04-12 | 2018-04-13 | 0.375
杨婧 | 手机端ipo分配人页面修改流程调整 | 手机端ipo分配人页面修改流程调整 | 2 | 4.5 | 2018-04-23 | 2018-04-24 | 2018-04-23 | 2018-04-24 | 1
杨婧 | 手机端报告查询和出差流程审批页面详情展示处理 | 手机端报告查询和出差流程审批页面详情展示处理 | 1 | 4 | 2018-04-25 | 2018-05-13 | 2018-04-25 | 2018-05-14 | 1.25 | 3 | 0.3125 | 0.2
杨婧 | 太平资产移动审批--普通债(一级市场投标)需求变更_20180502 | 太平资产移动审批--普通债(一级市场投标)需求变更_20180502 | 2 | 9 | 2018-05-03 | 2018-05-16 | 2018-05-04 | 2018-05-16 | 2.375 | 3 | 0.5 | 0.17391
杨婧 | 手机端审批页面增加低级错误统计 | 手机端审批页面增加低级错误统计 | 1.5 | 3 | 2018-05-08 | 2018-05-09 | 2018-05-08 | 2018-05-10 | 1.625
杨婧 | 太平资产移动审批--因私出国需求变更_20180507 | 太平资产移动审批--因私出国需求变更_20180507 | 1 | 6 | 2018-05-09 | 2018-05-16 | 2018-05-10 | 2018-05-14 | 0.375 | 7 | 1.525 | 0.80263
姚志昊 | 上市公司交流会功能调整需求变更(转移) | 上市公司交流会功能调整(转移) | 3 | 4 | 2017-12-22 | 2018-04-27 | 2018-02-26 | 2018-05-02 | 3.85 | 10 | 0.9375 | 0.19582
姚志昊 | 外部报告数据迁移 | 外部报告数据迁移 | 1 | 1 | 2018-03-29 | 2018-04-02 | 2018-03-30 | 2018-03-30 | 0.25 | 5
姚志昊 | 卖方观点-我的订阅 | 卖方观点-我的订阅 | 2 | 5 | 2018-04-03 | 2018-04-13 | 2018-04-10 | 2018-04-24 | 1.3125 | 6 | 0.675 | 0.33962
姚志昊 | 海富通网下申购审批新增提醒 | 海富通网下申购审批新增提醒 | 1 | 1 | 2018-04-18 | 2018-04-20 | 2018-04-18 | 2018-04-20 | 2 | 4 | 0.75 | 0.27273
姚志昊 | 客户检测的外部报告相关sql优化 | 客户检测的外部报告相关sql优化 | 2 | 2 | 2018-05-02 | 2018-05-04 | 2018-05-02 | 2018-05-03 | 0.6
姚志昊 | 海富通分销结果录入增加汇总统计 | 海富通分销结果录入增加汇总统计 | 0.5 | 0.5 | 2018-05-14 | 2018-05-14 | 2018-05-13 | 2018-05-14 | 0.5 | 3 | 0.5625 | 0.52941
姚志昊 | 外部报告新增评级变化条件 | 外部报告新增评级变化条件 | 3 | 3 | 2018-05-15 | 2018-05-18 | 2018-05-13 | 2018-05-28 | 2.2625 | 1 | 0.25 | 0.099502
姚志昊 | 兴全基金-外部报告隔离升级 | 兴全基金-外部报告隔离升级 | 0.5 | 0.5 | 2018-05-18 | 2018-05-18 | 2018-05-18 | 2018-05-18 | 0.4375
姚志昊 | 研究员打分需求变更 | 研究员打分需求变更 |  | 10 | 2018-05-22 | 2018-05-31 | 2018-05-21 | 2018-05-31 | 2.8
姚志昊 | 路演打分追加消息提醒 | 路演打分追加消息提醒 | 1 | 1 | 2018-05-29 | 2018-06-01 | 2018-05-28 | 2018-06-01 | 0.8125
姚志昊 | 研究员打分需求变更2 | 研究员打分需求变更 |  | 1 | 2018-06-05 | 2018-06-05 | 2018-06-06 | 2018-06-11 | 1.1125
姚志昊 | 中海外部报告迁移附件归档处理 | 中海外部报告迁移附件归档处理 | 2.5 | 2.5 | 2018-06-07 | 2018-06-09 | 2018-06-06 | 2018-06-11 | 1.625
姚志昊 | 中海外部报告迁移附件归档处理-20180613 | 中海外部报告迁移附件归档处理 | 1 | 1 | 2018-06-14 | 2018-06-21 | 2018-06-13 | 2018-06-15 | 1
姚志昊 | 研究员打分需求打分参数修改变更 | 研究员打分需求打分参数修改变更 | 1 | 1 | 2018-06-18 | 2018-06-20 | 2018-06-15 | 2018-06-20 | 1.3125
姚志昊 | 恒大信评-信用评级审批改造 | 恒大信评-信用评级审批改造 | 3 | 3 | 2018-06-21 | 2018-06-26 | 2018-06-22 | 2018-06-22 | 1.625 | 2 | 0.75 | 0.31579
姚志昊 | 后缀添加和页面修改需求（信评）_变更 | 后缀添加和页面修改需求（信评）_变更 | 2 | 2 | 2018-06-21 | 2018-06-21 | 2018-06-20 | 2018-06-21 | 1.3125
姚志昊 | 债券评级查询页面 | 债券评级查询页面 | 2 | 2 | 2018-06-25 | 2018-06-26 | 2018-06-26 | 2018-06-28 | 1.75
叶锐 | 股权系统新增现在移动端功能 | 股权系统新增现在移动端功能 | 1 | 1 | 2018-04-19 | 2018-04-19 | 2018-04-19 | 2018-04-20 | 1 | 4 | 1.2812 | 0.56164
袁汉林 | 新增券商路演 | 新增券商路演 | 4 | 10 | 2018-05-03 | 2018-05-11 | 2018-05-03 | 2018-06-05 | 5.7625 | 7 | 1.2625 | 0.17972
袁汉林 | 服务器客户-卖方客户匹配 | 服务器客户-卖方客户匹配 | 3 | 3 | 2018-06-12 | 2018-06-14 | 2018-06-12 | 2018-06-14 | 2.725 | 1
曾敏 | FOF组合规则配置开发 | FOF组合规则配置开发 | 15 | 15 | 2018-04-03 | 2018-04-20 | 2018-04-02 | 2018-04-23 | 4.75 | 10 | 1.5 | 0.24
曾敏 | 卖方观点-券商荐股 | 卖方观点-券商荐股 | 10 | 20 | 2018-04-03 | 2018-04-20 | 2018-04-03 | 2018-05-07 | 5.4375 | 30 | 4.475 | 0.45145
曾敏 | 组合清算定时任务通过配置文件参数控制是否开启 | 组合清算定时任务通过配置文件参数控制是否开启 | 2 | 2 | 2018-04-09 | 2018-04-12 | 2018-04-07 | 2018-04-08 | 1
曾敏 | 银河基金sirm组合管理定制话行业指标 | 银河基金sirm组合管理定制话行业指标 | 3 | 3 | 2018-04-10 | 2018-04-13 | 2018-04-11 | 2018-04-11 | 0.125
曾敏 | 银河sirm模拟组合查询页面及创建修改 | 银河sirm模拟组合查询页面及创建修改 | 1 | 1 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 | 0.25
曾敏 | 银河基金sirm组合管理定制话行业指标-20180411 | 银河基金sirm组合管理定制话行业指标 | 2 | 2 | 2018-04-11 | 2018-04-12 | 2018-04-12 | 2018-04-12 | 1
曾敏 | 投资组合基本版上线 | 投资组合基本版上线 | 1 | 1 | 2018-04-23 | 2018-04-23 | 2018-04-24 | 2018-04-24 | 0.75 | 6 | 1.3125 | 0.63636
曾敏 | 模拟组合基本版 | 模拟组合基本版 | 1 | 1 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 2018-04-24 | 0.25 | 4 | 0.25 | 0.5
曾敏 | 中融基金模拟组合历史组合数据处理需求-20180424 | 中融基金模拟组合历史组合数据处理需求 | 4 | 4 | 2018-04-26 | 2018-05-02 | 2018-04-26 | 2018-04-25 | 0.625 | 10 | 1.25 | 0.66667
曾敏 | 客户检测的持仓分析相关sql优化 | 客户检测的持仓分析相关sql优化 | 1 | 1 | 2018-05-02 | 2018-05-03 | 2018-05-04 | 2018-05-04 | 0.625
曾敏 | 银河基金sirm新增模拟组合数据监控功能 | 银河基金sirm新增模拟组合数据监控功能 | 2 | 2 | 2018-05-04 | 2018-05-08 | 2018-05-03 | 2018-05-03 | 0.375 | 2 | 0.1875 | 0.33333
曾敏 | 调整组合 | 调整组合 | 7 | 7 | 2018-05-09 | 2018-05-14 | 2018-05-10 | 2018-05-22 | 1.125 | 4 | 0.8125 | 0.41935
曾敏 | 前海开源sirm组合发布 | 前海开源sirm组合发布 | 2 | 2 | 2018-05-10 | 2018-05-15 | 2018-05-10 | 2018-05-11 | 1.5 | 4 | 0.25 | 0.14286
曾敏 | 我的组合组合查询 | 我的组合组合查询 | 5 | 5 | 2018-05-11 | 2018-05-14 | 2018-05-12 | 2018-05-22 | 4
曾敏 | 银河基金sirm模拟组合查询导出excel格式修改 | 银河基金sirm模拟组合查询导出excel格式修改 |  | 1 | 2018-05-15 | 2018-05-16 | 2018-05-16 | 2018-05-16 | 0.625 | 1 | 0.125 | 0.16667
曾敏 | 发布新版模拟组合港股组合 | 发布新版模拟组合港股组合 | 1 | 1 | 2018-05-22 | 2018-05-24 | 2018-05-25 | 2018-05-24 | 1
曾敏 | 调整组合-20180524 | 调整组合 | 7 | 7 | 2018-05-28 | 2018-06-07 | 2018-06-05 | 2018-06-05 | 0 | 4 | 0.8125 | 1
曾敏 | 我的组合组合查询-20180524 | 我的组合组合查询 | 5 | 5 | 2018-05-28 | 2018-06-07 | 2018-06-04 | 2018-06-05 | 2
曾敏 | 前海联合增加组合监控功能 | 前海联合增加组合监控功能 | 1 | 1 | 2018-05-31 | 2018-06-19 | 2018-05-31 | 2018-05-31 | 0.25 | 1 | 0.375 | 0.6
曾敏 | 恒大增加组合监控功能 | 恒大增加组合监控功能 | 1 | 1 | 2018-05-31 | 2018-06-19 | 2018-05-31 | 2018-06-01 | 0.125
曾敏 | 安信增加组合监控功能 | 安信增加组合监控功能 | 1 | 1 | 2018-05-31 | 2018-06-19 | 2018-05-31 | 2018-05-31 | 0.375
曾敏 | 富荣基金增加组合监控功能 | 富荣基金增加组合监控功能 | 1 | 1 | 2018-05-31 | 2018-06-19 | 2018-05-31 | 2018-05-31 | 0.125 | 2 | 0.625 | 0.83333
曾敏 | 组合新增修改调池生成命令数据 | 组合新增修改调池生成命令数据 | 3 | 3 | 2018-06-06 | 2018-06-10 | 2018-06-06 | 2018-06-07 | 1.25
曾敏 | 模拟组合分红信息 | 模拟组合分红信息 | 2 | 2 | 2018-06-11 | 2018-06-15 | 2018-06-11 | 2018-06-11 | 0.875
曾敏 | 组合阶段导入功能修复 | 组合阶段导入功能修复 | 3 | 3 | 2018-06-12 | 2018-06-14 | 2018-06-12 | 2018-06-12 | 1.125 | 2 | 0.15 | 0.11765
曾敏 | 港股分红数据处理 | 港股分红数据处理 | 1 | 1 | 2018-06-15 | 2018-06-15 | 2018-06-15 | 2018-06-21 | 0.75
曾雄 | 分管行业开发 | 分管行业开发 | 5 | 5 | 2018-04-30 | 2018-05-09 | 2018-04-27 | 2018-05-04 | 4 | 2 | 0.2125 | 0.050445
曾雄 | 统计分析/账户维护与持仓分析 | 统计分析/账户维护与持仓分析 | 13 | 13 | 2018-05-07 | 2018-05-18 | 2018-05-07 | 2018-05-16 | 8.075 | 7 | 1.1125 | 0.12109
曾雄 | 临时代码 | 临时代码 | 3 | 3 | 2018-05-16 | 2018-05-20 | 2018-05-16 | 2018-05-21 | 3.5 | 17 | 1.6 | 0.31373
曾雄 | 主体全景图 | 主体全景图 | 2 | 2 | 2018-05-21 | 2018-05-22 | 2018-05-21 | 2018-05-24 | 2.3875 | 4 | 0.35 | 0.12785
曾雄 | 财务数据 | 财务数据 | 2 | 2 | 2018-05-23 | 2018-05-25 | 2018-05-24 | 2018-05-25 | 2.125 | 4 | 0.8875 | 0.29461
曾雄 | 债券信息查询 | 债券信息查询 | 2 | 2 | 2018-05-25 | 2018-05-29 | 2018-05-29 | 2018-05-30 | 2.25 | 14 | 0.8625 | 0.27711
曾雄 | 临时代码管理新 | 临时代码管理新 | 3 | 3 | 2018-06-06 | 2018-06-08 | 2018-06-06 | 2018-06-10 | 4.125
章烈锋 | 公告点评变更 | 公告点评变更 | 4 | 4 | 2018-04-24 | 2018-04-27 | 2018-04-24 | 2018-05-07 | 3.25
章烈锋 | 工银瑞信大屏幕策略会显示 | 工银瑞信大屏幕策略会显示 | 4 | 4 | 2018-05-02 | 2018-05-09 | 2018-05-02 | 2018-05-16 | 3.875
张邓 | 创建评级期优化 | 创建评级期优化 | 4 | 4 | 2018-04-10 | 2018-04-13 | 2018-04-11 | 2018-04-13 | 2.25 | 2 | 0.125 | 0.052632
张邓 | 监管新闻优化(转移) | 监管新闻优化(转移) | 1 | 1 | 2018-04-12 | 2018-04-17 | 2018-04-12 | 2018-04-13 | 0.625 | 1 | 0.125 | 0.16667
张邓 | 信评项目换was服务器相关war包修改 | 信评项目换was服务器相关war包修改 | 3 | 3 | 2018-04-18 | 2018-04-20 | 2018-04-18 | 2018-04-19 | 0.75
张邓 | 国投信评bug调整 | 国投信评bug调整 | 1 | 1 | 2018-04-18 | 2018-04-20 | 2018-04-19 | 2018-04-19 | 0.875 | 1 | 0.125 | 0.125
张烈 | 汇丰入库关联附件须生成内部报告-历史数据处理 | 汇丰入库关联附件须生成内部报告-历史数据处理 | 2 | 2 | 2018-04-02 | 2018-04-04 | 2018-03-30 | 2018-04-02 | 2 | 5 | 0.625 | 0.2381
张烈 | 债券调整中出库和移库的操作变更需求 | 债券调整中出库和移库的操作变更需求 | 2 | 2 | 2018-04-03 | 2018-04-08 | 2018-04-02 | 2018-04-08 | 1.5625 | 10 | 1.8125 | 0.53704
张烈 | 评级调整通知事宜 | 评级调整通知事宜 | 3 | 3 | 2018-04-10 | 2018-04-13 | 2018-04-09 | 2018-04-12 | 3
张烈 | 量化股票池 | 量化股票池 | 2 | 2 | 2018-04-13 | 2018-04-16 | 2018-04-13 | 2018-04-16 | 2 | 2 | 0.375 | 0.15789
张烈 | 携宁基金池和赢时胜基金池对接需求 | 携宁基金池和赢时胜基金池对接需求 | 4 | 4 | 2018-04-17 | 2018-04-20 | 2018-04-17 | 2018-04-20 | 3.25 | 5 | 0.5625 | 0.14754
张烈 | 调池页面增加债券数据展示 | 调池页面增加债券数据展示 | 1 | 1 | 2018-04-23 | 2018-04-25 | 2018-04-23 | 2018-04-25 | 1 | 2 | 0.125 | 0.11111
张烈 | 银河基金sirm增加退市股票自动出池定时任务 | 银河基金sirm增加退市股票自动出池定时任务 | 1 | 1 | 2018-04-24 | 2018-04-26 | 2018-04-23 | 2018-04-25 | 0.875
张烈 | 中银-投资池调整 | 中银-投资池调整 | 4 | 4 | 2018-04-27 | 2018-05-03 | 2018-04-26 | 2018-05-03 | 4 | 3 | 0.1875 | 0.044776
张烈 | 投资池导出支持o32格式的excle功能，新增一个导出功能菜单 | 投资池导出支持o32格式的excle功能，新增一个导出功能菜单 | 1 | 1 | 2018-04-27 | 2018-04-27 | 2018-04-25 | 2018-04-26 | 1
张烈 | 股票、债券excel调整增加调整原因 | 股票、债券excel调整增加调整原因 | 2 | 2 | 2018-05-07 | 2018-05-10 | 2018-05-04 | 2018-05-05 | 1.5 | 2 | 0.025 | 0.016393
张烈 | 精选池临时代码单独流程和城投债展示优化 | 精选池临时代码单独流程和城投债展示优化 |  | 6 | 2018-05-07 | 2018-05-16 | 2018-05-07 | 2018-05-10 | 3 | 4 | 0.9375 | 0.2381
张烈 | 后缀添加和页面修改需求（投资池） | 后缀添加和页面修改需求（投资池） | 5 | 5 | 2018-05-09 | 2018-05-15 | 2018-05-10 | 2018-05-15 | 3.3125 | 12 | 0.6875 | 0.17188
张烈 | 查询页面增加列审批完成日期 | 查询页面增加列审批完成日期 | 1 | 1 | 2018-05-15 | 2018-05-18 | 2018-05-15 | 2018-05-16 | 0.25
张烈 | 中海投资池控件调整 | 中海投资池控件调整 | 1 | 1 | 2018-05-16 | 2018-05-17 | 2018-05-16 | 2018-05-17 | 1
张烈 | 华安基金-QDII股票池 | 华安基金-QDII股票池 | 3 | 3 | 2018-05-17 | 2018-05-23 | 2018-05-18 | 2018-05-23 | 2.1875 | 1 | 0.25 | 0.10256
张烈 | 债券池excel导入支持债券种类填写大类型 | 债券池excel导入支持债券种类填写大类型 | 1 | 1 | 2018-05-22 | 2018-05-25 | 2018-05-23 | 2018-05-23 | 0.375
张烈 | 中海投资池控件调整-20180523 | 中海投资池控件调整 | 1 | 1 | 2018-05-24 | 2018-05-30 | 2018-05-24 | 2018-05-24 | 1
张烈 | 投资池单券入池流程定制 | 投资池单券入池流程定制 | 2 | 2 | 2018-05-28 | 2018-05-29 | 2018-05-25 | 2018-05-29 | 2 | 2 | 0.4375 | 0.17949
张烈 | 华安基金-股票池 | 华安基金-股票池 | 0.5 | 0.5 | 2018-05-29 | 2018-05-30 | 2018-05-30 | 2018-05-29 | 0.3125
张烈 | 股票池&债券池 | 股票池&债券池 | 5 | 5 | 2018-05-29 | 2018-06-11 | 2018-05-29 | 2018-06-08 | 5 | 4 | 0.25 | 0.047619
张烈 | 精选池临时代码单独流程和城投债展示优化-20180601 | 精选池临时代码单独流程和城投债展示优化 | 2 | 2 | 2018-06-04 | 2018-06-06 | 2018-06-05 | 2018-06-06 | 1.375 | 4 | 0.9375 | 0.40541
张烈 | 关联方债券禁止池优化 | 关联方债券禁止池优化 | 2 | 2 | 2018-06-05 | 2018-06-07 | 2018-06-06 | 2018-06-07 | 1.125
张烈 | 投资池excel导入功能，添加导出失败的证券 | 投资池excel导入功能，添加导出失败的证券 | 2 | 2 | 2018-06-13 | 2018-06-14 | 2018-06-12 | 2018-06-13 | 1.75 | 1 | 0.125 | 0.066667
张强 | 行业数据迁移 | 行业数据迁移 | 3 | 3 | 2018-04-05 | 2018-04-09 | 2018-04-04 | 2018-04-09 | 1.625 | 8 | 0.5625 | 0.25714
张强 | 评级调整通知 | 评级调整通知 | 1 | 2 | 2018-04-11 | 2018-04-13 | 2018-04-13 | 2018-04-16 | 1.25 | 1 | 0 | 0
张强 | 估值模型升级（历史报告评级和目标价保留及合规更新） | 估值模型升级（历史报告评级和目标价保留及合规更新） | 1 | 2 | 2018-04-12 | 2018-04-16 | 2018-04-13 | 2018-04-16 | 1 | 7 | 1.375 | 0.57895
张强 | 百年资管sirm券商路演定制化需求 | 百年资管sirm券商路演定制化需求 | 10 | 10 | 2018-04-16 | 2018-04-28 | 2018-04-17 | 2018-04-28 | 8.375 | 16 | 2.0625 | 0.1976
张强 | 汇添富2018年4月重点池股票180天无报告提醒 | 汇添富2018年4月重点池股票180天无报告提醒 | 1 | 1 | 2018-04-17 | 2018-04-18 | 2018-04-17 | 2018-04-17 | 1 | 4 | 0.125 | 0.11111
张强 | 合规对接导出相应的报告数据-20180425 | 合规对接导出相应的报告数据 | 1 | 1 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-27 | 1 | 2 | 0.1875 | 0.15789
张强 | 客户检测的行业股票研究相关sql优化 | 客户检测的行业股票研究相关sql优化 | 3 | 7 | 2018-05-04 | 2018-05-11 | 2018-05-04 | 2018-05-10 | 1.375
张强 | 银河基金sirm股票行业分管权限复制 | 银河基金sirm股票行业分管权限复制 | 2 | 2 | 2018-05-04 | 2018-05-07 | 2018-05-04 | 2018-05-07 | 1.6875 | 3 | 0.5 | 0.22857
张强 | 重仓股推荐 | 重仓股推荐 | 3 | 3 | 2018-05-07 | 2018-05-10 | 2018-05-08 | 2018-05-11 | 2 | 5 | 1.4375 | 0.41818
张强 | 信评内部报告修改需求-20180508 | 信评内部报告修改需求 | 0.5 | 1 | 2018-05-09 | 2018-05-10 | 2018-05-08 | 2018-05-08 |  | 11 | 0.4625
张强 | 重仓股推荐考核 | 重仓股推荐考核 | 5 | 5 | 2018-05-10 | 2018-05-18 | 2018-05-08 | 2018-05-23 | 5 | 2 | 0.375 | 0.069767
张强 | 行业评级历史查询展示增加一列展示相邻两次评级时间范围内指标的涨跌幅 | 行业评级历史查询展示增加一列展示相邻两次评级时间范围内指标的涨跌幅 | 3 | 3 | 2018-05-18 | 2018-06-01 | 2018-06-03 | 2018-06-03 | 0.625 | 2 | 0.0625 | 0.090909
张强 | 银河基金sirm内部报告模板修改 | 银河基金sirm内部报告模板修改 | 2 | 4 | 2018-05-24 | 2018-05-25 | 2018-05-24 | 2018-05-25 |  | 1 | 0.25
张强 | 广发-英文报告模板开发和解析-尾页声明变更 | 广发-英文报告模板开发和解析 | 2 | 10 | 2018-05-24 | 2018-06-05 | 2018-05-24 | 2018-05-31 | 1.5 | 22 | 1.25 | 0.45455
张强 | 报告类型模板分类 | 报告类型模板分类 | 5 | 5 | 2018-05-28 | 2018-06-01 | 2018-05-29 | 2018-06-03 | 2.75 | 6 | 1.3125 | 0.32308
张强 | 报告插件选择作者需求变更 | 报告插件选择作者需求变更 | 1 | 2 | 2018-06-04 | 2018-06-04 | 2018-06-03 | 2018-06-04 |  | 4 | 0.875
张强 | 股票认领-20180604 | 股票认领 | 1 | 1 | 2018-06-05 | 2018-06-05 | 2018-06-04 | 2018-06-04 | 0.5 | 2 | 0.25 | 0.33333
张强 | 报告转换PDF功能优化 | 报告转换PDF功能优化 | 3 | 3 | 2018-06-05 | 2018-06-07 | 2018-05-23 | 2018-06-07 | 2.625 | 1 | 0 | 0
张强 | 行业评级历史查询展示增加一列展示相邻两次评级时间范围内指标的涨跌幅-20180621 | 行业评级历史查询展示增加一列展示相邻两次评级时间范围内指标的涨跌幅 | 0.5 | 0.5 | 2018-06-22 | 2018-06-22 | 2018-06-21 | 2018-06-20 | 0 | 2 | 0.0625 | 1
张庆龙 | 组合管理指标函数优化与改造 | 组合管理指标函数优化与改造 | 2 | 12 | 2018-04-16 | 2018-04-20 | 2018-04-16 | 2018-04-20 | 0.25 | 5 | 0.375 | 0.6
张帅 | 招商需求工作单-活动流程，查询，统计 | 招商需求工作单-活动流程，查询，统计 | 5 | 5 | 2018-03-28 | 2018-04-01 | 2018-03-29 | 2018-03-30 | 3 | 21 | 1.5375 | 0.33884
张帅 | 招商工作单-会议室接口对接 | 招商工作单-会议室接口对接 | 5 | 5 | 2018-04-02 | 2018-04-06 | 2018-04-04 | 2018-04-09 | 1.55 | 1 | 0.4375 | 0.22013
张帅 | 招商活动预约增加抄送中台消息提醒 | 招商活动预约增加抄送中台消息提醒 | 2 | 2 | 2018-04-02 | 2018-04-04 | 2018-04-03 | 2018-04-02 | 0.5
张帅 | 账号离职和用户同步记录查看 | 账号离职和用户同步记录查看 | 3 | 9 | 2018-05-03 | 2018-05-18 | 2018-05-03 | 2018-05-22 | 3.25 | 6 | 0.575 | 0.15033
张帅 | 投研交互屏蔽微信报错 | 投研交互屏蔽微信报错 | 5 | 5 | 2018-05-23 | 2018-05-28 | 2018-05-23 | 2018-05-23 | 1.25
张帅 | 投研交互邮件提醒待处理活动 | 投研交互邮件提醒待处理活动 | 3 | 3 | 2018-05-24 | 2018-05-30 | 2018-05-24 | 2018-05-29 | 2.625 | 1 | 0.075 | 0.027778
张帅 | 投研交互app页面跳转和增加活动查询条件 | 投研交互app页面跳转和增加活动查询条件 | 2 | 2 | 2018-05-24 | 2018-06-01 | 2018-05-23 | 2018-05-23 | 0.5
张帅 | 0528三个日程页面增加导出功能 | 0528三个日程页面增加导出功能 | 3 | 3 | 2018-05-30 | 2018-06-01 | 2018-05-31 | 2018-06-04 | 2.8875
张扬 | 新框架菜单管理功能开发 | 新框架菜单管理功能开发 | 2 | 2 | 2018-04-08 | 2018-04-10 | 2018-04-08 | 2018-04-10 | 3 | 10 | 1.25 | 0.29412
张扬 | 新框架用户管理和用户菜单权限配置 | 新框架用户管理和用户菜单权限配置 | 3 | 3 | 2018-04-11 | 2018-04-13 | 2018-04-11 | 2018-04-13 | 3 | 7 | 1 | 0.25
张扬 | 新框架中角色管理功能开发 | 新框架中角色管理功能开发 | 1 | 1 | 2018-04-16 | 2018-04-16 | 2018-04-16 | 2018-04-16 | 1 | 6 | 0.375 | 0.27273
张扬 | 新框架中SQL方案配置功能 | 新框架中SQL方案配置功能 | 6 | 6 | 2018-04-17 | 2018-04-24 | 2018-04-17 | 2018-04-24 | 6 | 4 | 0.75 | 0.11111
张扬 | EXCEL模板分类迁移 | EXCEL模板分类迁移 | 1 | 1 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | 1 | 7 | 0.375 | 0.27273
张扬 | EXCEL报表模板迁移 | EXCEL报表模板迁移 | 2 | 2 | 2018-04-26 | 2018-04-27 | 2018-04-26 | 2018-04-27 | 2 | 4 | 0.25 | 0.11111
张扬 | EXCEL模板编码维护迁移 | EXCEL模板编码维护迁移 | 1 | 1 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 2018-04-28 | 1
张扬 | 权限功能迁移 | 权限功能迁移 | 5 | 5 | 2018-05-14 | 2018-05-18 | 2018-05-15 | 2018-05-18 | 3 | 9 | 0.75 | 0.2
张扬 | 数据补录配置功能迁移 | 数据补录配置功能迁移 | 4 | 4 | 2018-05-22 | 2018-05-25 | 2018-05-22 | 2018-05-25 | 3.625 | 15 | 1 | 0.21622
张扬 | 数据补录功能迁移 | 数据补录功能迁移 | 6 | 6 | 2018-05-28 | 2018-06-05 | 2018-05-29 | 2018-06-05 | 5.625 | 11 | 1.0625 | 0.15888
张洋洋 | 公司及托管人关联方名单 | 公司及托管人关联方名单 | 7 | 9 | 2018-03-05 | 2018-04-12 | 2018-03-05 | 2018-03-26 | 8 | 7 | 1.25 | 0.13514
张洋洋 | 股票行业分管，盈利预测数据迁移 | 股票行业分管，盈利预测数据迁移 | 3 | 3 | 2018-03-28 | 2018-04-02 | 2018-03-28 | 2018-04-02 | 2.9375 | 10 | 1.5125 | 0.33989
张洋洋 | 海富通一级池入池报告到期检查调整 | 海富通一级池入池报告到期检查调整 | 4 | 4 | 2018-04-03 | 2018-04-08 | 2018-04-03 | 2018-04-04 | 2.75 | 11 | 0.75 | 0.21429
张洋洋 | 银河基金sirm升级业绩点评导入表格修改 | 银河基金sirm升级业绩点评导入表格修改 | 1 | 1 | 2018-04-05 | 2018-04-08 | 2018-04-08 | 2018-04-08 | 0.625 | 6 | 0.225 | 0.26471
张洋洋 | 公司及托管人关联方名单2 | 公司及托管人关联方名单 | 5 | 5 | 2018-04-12 | 2018-04-20 | 2018-04-11 | 2018-04-13 | 2.8375 | 7 | 1.25 | 0.30581
张洋洋 | 投资池入库，审批时，审批默认选项改成审批通过 | 投资池入库，审批时，审批默认选项改成审批通过 | 0.5 | 0.5 | 2018-04-16 | 2018-04-16 | 2018-04-16 | 2018-04-16 | 0.75 | 2 | 0.15 | 0.16667
张洋洋 | 百年资管sirm支持恒生o32格式的excel导出 | 百年资管sirm支持恒生o32格式的excel导出 | 2 | 2 | 2018-04-17 | 2018-04-19 | 2018-04-17 | 2018-04-18 | 1.6875 | 11 | 1.1875 | 0.41304
张洋洋 | 银河基金sirm | 银河基金sirm | 2 | 3 | 2018-04-19 | 2018-04-23 | 2018-04-20 | 2018-04-23 | 2.3875 | 1 | 0.0125 | 0.0052083
张洋洋 | 公司及托管人关联方名单3 | 公司及托管人关联方名单 | 1 | 1 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 2018-04-20 | 0.375 | 7 | 1.25 | 0.76923
张洋洋 | 债券研究查询优化-股票研究 | 债券研究查询优化 | 1 | 1 | 2018-04-23 | 2018-04-25 | 2018-04-24 | 2018-04-24 | 0.9875
张洋洋 | 华泰柏瑞个股推荐需求变更 | 华泰柏瑞个股推荐需求变更 | 3 | 3 | 2018-04-25 | 2018-04-27 | 2018-04-26 | 2018-04-26 | 1.325 | 6 | 0.4375 | 0.24823
张洋洋 | 盈利预测数据调整建议 | 盈利预测数据调整建议 | 2 | 2 | 2018-04-26 | 2018-04-28 | 2018-04-27 | 2018-04-27 | 1 | 1 | 0.0125 | 0.012346
张洋洋 | 公司及托管人关联方名单4 | 公司及托管人关联方名单 | 3 | 3 | 2018-04-30 | 2018-05-07 | 2018-05-02 | 2018-05-03 | 1.9875 | 7 | 1.25 | 0.3861
张洋洋 | 股票、债券excel调整增加调整原因1 | 股票、债券excel调整增加调整原因 | 1 | 1 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 2018-05-04 | 1 | 2 | 0.025 | 0.02439
张洋洋 | 股票认领 | 股票认领 | 3 | 3 | 2018-05-07 | 2018-05-10 | 2018-05-07 | 2018-05-09 | 2.875 | 2 | 0.25 | 0.08
张洋洋 | 债券报告撰写优化功能 | 债券报告撰写优化功能 | 1 | 1 | 2018-05-08 | 2018-05-11 | 2018-05-10 | 2018-05-11 | 1.05 | 2 | 0.0625 | 0.05618
张洋洋 | 长盛行业配置需求 | 长盛行业配置需求 | 6 | 8 | 2018-05-09 | 2018-05-18 | 2018-05-11 | 2018-05-16 | 3.1875 | 7 | 1.3125 | 0.29167
张洋洋 | 银河基金sirm业绩点评增加列 | 银河基金sirm业绩点评增加列 | 2 | 2 | 2018-05-16 | 2018-05-17 | 2018-05-16 | 2018-05-16 | 0.6875 | 5 | 0.0875 | 0.1129
张洋洋 | 关联方功能相关优化需求 | 关联方功能相关优化需求 | 2 | 2 | 2018-05-18 | 2018-05-22 | 2018-05-18 | 2018-05-25 | 4.825 | 7 | 0.975 | 0.1681
张芸芸 | 广发-APP报告审批-基本版 | 广发-APP报告审批-基本版 | 3 | 8 | 2018-04-20 | 2018-04-26 | 2018-04-20 | 2018-05-31 | 2.5 | 35 | 3.2 | 0.5614
张芸芸 | 广发英文报告发送配置 | 广发英文报告发送配置 | 2 | 2 | 2018-05-03 | 2018-05-09 | 2018-05-03 | 2018-05-07 | 1.25 | 6 | 0.5 | 0.28571
张芸芸 | 路演预约添加专家交流类型 | 路演预约添加专家交流类型 | 1 | 2 | 2018-05-08 | 2018-05-08 | 2018-05-07 | 2018-05-07 | 1 | 5 | 0.375 | 0.27273
张芸芸 | 广发-股票分管增加覆盖功能 | 广发-股票分管增加覆盖功能 | 1 | 1 | 2018-05-09 | 2018-05-09 | 2018-05-11 | 2018-05-10 | 0.875 | 3 | 0.375 | 0.3
张芸芸 | 广发-报告作者和联系人 | 广发-报告作者和联系人 | 2 | 2 | 2018-05-10 | 2018-05-21 | 2018-05-14 | 2018-05-18 | 2.0625 | 4 | 0.5 | 0.19512
张芸芸 | 广发-路演预约PC、APP端需求变更 | 广发-路演预约PC、APP端需求变更 | 3 | 3 | 2018-05-17 | 2018-05-21 | 2018-05-18 | 2018-05-18 | 1.125 | 9 | 1 | 0.47059
赵公平 | 组合管理指标函数优化与改造 | 组合管理指标函数优化与改造 | 5 | 12 | 2018-04-16 | 2018-04-20 | 2018-04-16 | 2018-04-20 | 4.875 | 5 | 0.375 | 0.071429
赵凯军 | 事件驱动定时任务通过配置文件参数控制是否开启 | 事件驱动定时任务通过配置文件参数控制是否开启 | 3 | 3 | 2018-04-10 | 2018-04-13 | 2018-04-17 | 2018-05-04 | 2 | 1 | 0.075 | 0.036145
郑雄 | 数据同步 | 数据同步 | 14 | 14 | 2018-03-26 | 2018-04-13 | 2018-03-27 | 2018-04-10 | 8.375 | 18 | 3 | 0.26374
周朗 | 元数据管理-枚举配置功能开发 | 元数据管理-枚举配置功能开发 | 3 | 3 | 2018-06-13 | 2018-06-15 | 2018-06-12 | 2018-06-14 | 3.5 | 4 | 0.5 | 0.125
朱思琴 | 债券入池，wind与聚源关系 | 债券入池，wind与聚源关系 | 10 | 10 | 2018-05-08 | 2018-05-18 | 2018-05-07 | 2018-06-13 | 3.3875
朱思琴 | 主体关联管理(转移) | 主体关联管理(转移) | 2 | 2 | 2018-05-09 | 2018-05-14 | 2018-05-10 | 2018-05-11 | 1.625
朱思琴 | 集团关系管理(转移) | 集团关系管理(转移) | 2 | 2 | 2018-05-14 | 2018-05-16 | 2018-05-14 | 2018-05-14 | 1 | 3 | 0 | 0
朱思琴 | 授信额度管理(转移) | 授信额度管理(转移) | 2 | 2 | 2018-05-15 | 2018-05-16 | 2018-05-14 | 2018-05-15 | 1 | 4 | 0.375 | 0.27273
朱思琴 | 额度同步(转移) | 额度同步(转移) | 2 | 2 | 2018-05-17 | 2018-05-18 | 2018-05-16 | 2018-05-17 | 2 | 3 | 0.075 | 0.036145
朱思琴 | 恒大信评-授信管理功能 | 恒大信评-授信管理功能 | 6 | 6 | 2018-05-21 | 2018-05-27 | 2018-05-18 | 2018-05-25 | 4.75 | 9 | 0.75 | 0.13636
朱思琴 | 恒大信评-负面新闻改造 | 恒大信评-负面新闻改造 | 4 | 4 | 2018-05-25 | 2018-06-05 | 2018-05-28 | 2018-06-04 | 4.25 | 6 | 1.0625 | 0.2
朱思琴 | 恒大信评-持仓与授信情况 | 恒大信评-持仓与授信情况 | 1 | 1 | 2018-05-25 | 2018-05-31 | 2018-05-25 | 2018-05-25 | 0.875 | 3 | 0.25 | 0.22222
朱思琴 | 恒大信评-授信管理功能-20180528 | 恒大信评-授信管理功能 | 2 | 2 | 2018-05-29 | 2018-06-01 | 2018-05-29 | 2018-05-29 | 0.5 | 9 | 0.75 | 0.6
朱勇 | 补单申请查询 | 补单申请查询 | 2 | 2 | 2018-03-29 | 2018-04-02 | 2018-03-29 | 2018-04-02 | 1.25
朱勇 | Matrix系统推送报告合并字段 | Matrix系统推送报告合并字段 | 1 | 1 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | 0.5
朱勇 | 行业公司更新报告锁定功能 | 行业公司更新报告锁定功能 | 2 | 2 | 2018-04-03 | 2018-04-08 | 2018-04-02 | 2018-04-03 | 0.75
朱勇 | 电话会议修改 | 电话会议修改 | 3 | 3 | 2018-04-08 | 2018-04-11 | 2018-04-03 | 2018-04-09 | 2.875
朱勇 | 电话会议检测短信时间是否一致 | 电话会议检测短信时间是否一致 | 1 | 1 | 2018-04-10 | 2018-04-11 | 2018-04-04 | 2018-04-10 | 1
朱勇 | Matrix重新推送联合调研功能 | Matrix重新推送联合调研功能 | 1 | 1 | 2018-04-11 | 2018-04-12 | 2018-04-10 | 2018-04-11 | 1
朱勇 | 合规——关键字管理，增加搜索功能 | 合规——关键字管理，增加搜索功能 | 1 | 1 | 2018-04-12 | 2018-04-13 | 2018-04-11 | 2018-04-12 | 0.75
朱勇 | 新增Matrix数据单一推送功能（所有） | 新增Matrix数据单一推送功能（所有） | 2 | 2 | 2018-04-13 | 2018-04-16 | 2018-04-12 | 2018-04-16 | 0.75
朱勇 | 广发-佣金导入 | 广发-佣金导入 | 3 | 3 | 2018-04-19 | 2018-04-20 | 2018-04-19 | 2018-04-23 | 2.25 | 61 | 1.0625 | 0.32075
朱勇 | 佣金管理 | 佣金管理 | 5 | 15 | 2018-04-24 | 2018-05-04 | 2018-05-07 | 2018-05-07 | 0
鄢晗茹 | 报告模版需求分析 | 报告模版需求分析 | 1 | 9 | 2018-04-03 | 2018-04-13 | 2018-04-03 | 2018-04-13 | 1 | 11 | 3.375 | 0.77143
鄢晗茹 | 债券报告提交-20180403 | 债券报告提交 | 0.5 | 0.5 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 2018-04-03 | 0.5 | 2 | 0.05 | 0.090909
鄢晗茹 | 根据资格证书区分写报告权限 | 根据资格证书区分写报告权限 | 3 | 3 | 2018-04-05 | 2018-04-10 | 2018-04-04 | 2018-04-09 | 2.6125 | 3 | 0.25 | 0.087336
鄢晗茹 | 审批报告时点击通过弹框提醒 | 审批报告时点击通过弹框提醒 | 0.5 | 1 | 2018-04-11 | 2018-04-12 | 2018-04-11 | 2018-04-11 | 0.5
鄢晗茹 | 债券主体报告功能优化_20180411 | 债券主体报告功能优化_20180411 | 1 | 3 | 2018-04-12 | 2018-04-16 | 2018-04-12 | 2018-04-13 | 1 | 1 | 0.025 | 0.02439
鄢晗茹 | 东方投研债券报告模板及报告提交解析解析 | 东方投研债券报告模板及报告提交解析解析 | 3 | 7 | 2018-04-16 | 2018-04-24 | 2018-04-16 | 2018-04-19 | 1.95 | 6 | 0.7875 | 0.28767
鄢晗茹 | 内部报告提交修改_20180418 | 内部报告提交修改_20180418 | 1 | 1 | 2018-04-20 | 2018-04-20 | 2018-04-19 | 2018-04-19 | 0.5
鄢晗茹 | 广发-报告类型英文维护 | 广发-报告类型英文维护 | 0.5 | 0.5 | 2018-05-08 | 2018-05-09 | 2018-05-07 | 2018-05-07 | 0.025
鄢晗茹 | 广发-港股行业对应关系 | 广发-港股行业对应关系 | 1 | 2 | 2018-05-08 | 2018-05-09 | 2018-05-09 | 2018-05-09 | 0.9375 | 1 | 0 | 0
鄢晗茹 | 报告查询添加主体查询 | 报告查询添加主体查询 | 0.5 | 0.5 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | 0.5 | 1 | 0.0625 | 0.11111
鄢晗茹 | 报告需求-20180509 | 报告需求 | 1 | 1 | 2018-05-09 | 2018-05-10 | 2018-05-09 | 2018-05-09 | 0.375 | 65 | 4.25 | 0.91892
鄢晗茹 | 广发-报告解析 | 广发-报告解析 | 3 | 3 | 2018-05-14 | 2018-05-21 | 2018-05-14 | 2018-05-21 | 2.9375 | 2 | 0.125 | 0.040816
鄢晗茹 | 报告默认等级 | 报告默认等级 | 1 | 1 | 2018-05-17 | 2018-05-21 | 2018-05-16 | 2018-05-16 | 0.875
鄢晗茹 | 中泰证券-合规修改201805 | 中泰证券-合规修改201805 | 3 | 3 | 2018-05-18 | 2018-05-22 | 2018-05-18 | 2018-05-22 | 2.0625 | 6 | 0.575 | 0.21801
鄢晗茹 | 内部报告不进行隔离墙检查 | 内部报告不进行隔离墙检查 | 1 | 1 | 2018-05-23 | 2018-05-25 | 2018-05-23 | 2018-05-23 | 0.625 | 2 | 0.025 | 0.038462
鄢晗茹 | 晨报控置提交时间和自动审批需求 | 晨报控置提交时间和自动审批需求 | 2 | 3 | 2018-05-23 | 2018-05-24 | 2018-05-23 | 2018-05-24 | 1.125 | 4 | 0.3125 | 0.21739
鄢晗茹 | 招商内部报告，菜单以及功能路径全部优化为相对路径 | 招商内部报告，菜单以及功能路径全部优化为相对路径 | 2 | 2 | 2018-05-24 | 2018-05-25 | 2018-05-24 | 2018-05-25 | 1.075
鄢晗茹 | 报告需求-报告附件名称规范变更 | 报告需求 | 1 | 1 | 2018-05-25 | 2018-05-29 | 2018-05-28 | 2018-05-28 | 0.5 | 65 | 4.25 | 0.89474
鄢晗茹 | 报告需求-附件转pdf逻辑调整 | 报告需求 | 2 | 10 | 2018-05-25 | 2018-05-30 | 2018-05-28 | 2018-05-28 | 8.2625 | 65 | 4.25 | 0.33966
鄢晗茹 | 广发-英文报告编辑 | 广发-英文报告编辑 | 4 | 4 | 2018-05-29 | 2018-06-01 | 2018-05-29 | 2018-05-31 | 2.6625 | 1 | 0.0625 | 0.022936
鄢晗茹 | 广发-报告需求补充 | 广发-报告需求补充 | 2 | 2 | 2018-06-04 | 2018-06-05 | 2018-06-02 | 2018-06-04 | 2 | 2 | 0.375 | 0.15789
鄢晗茹 | 手机合规后台接口协助 | 手机合规后台接口协助 | 1 | 2 | 2018-06-06 | 2018-06-07 | 2018-06-06 | 2018-06-06 |  | 1 | 0.125
鄢晗茹 | 报告审批流程意见字数优化 | 报告审批流程意见字数优化 | 1 | 1 | 2018-06-07 | 2018-06-07 | 2018-06-06 | 2018-06-06 | 1
鄢晗茹 | 广发-报告分析师承诺 | 广发-报告分析师承诺 | 1 | 1 | 2018-06-15 | 2018-06-15 | 2018-06-15 | 2018-06-15 | 0.45 | 2 | 0.125 | 0.21739
鄢晗茹 | 广发-APP报告权限 | 广发-APP报告权限 | 1 | 1 | 2018-06-19 | 2018-06-20 | 2018-06-19 | 2018-06-20 | 0.8125 | 1 | 0.0625 | 0.071429
鄢晗茹 | 广发-报告查询补充 | 广发-报告查询补充 | 2 | 2 | 2018-06-20 | 2018-06-22 | 2018-06-20 | 2018-06-22 | 1.3625 | 4 | 0.5 | 0.26846
鄢晗茹 | 广发-报告详情接口 | 广发-报告详情接口 | 2 | 2 | 2018-06-22 | 2018-06-26 | 2018-06-22 | 2018-06-22 | 0.625 | 1 | 0.125 | 0.16667
瞿立 | 舆情新页面功能开发 | 舆情新页面功能开发 | 4 | 4 | 2018-04-09 | 2018-04-12 | 2018-04-10 | 2018-04-13 | 4.1875 | 8 | 1.7125 | 0.29025
瞿立 | 2.1版本需求优化1-20180425 | 2.1版本需求优化1 | 1 | 1 | 2018-04-25 | 2018-04-25 | 2018-05-03 | 2018-05-03 | 0.5625 | 2 | 0.6875 | 0.55

## SQL
select t1.orgname as 姓名 , t3.name as 开发任务名称 , t3.requirementname as 需求名称 , t3.taskownerWorkload as 分配任务的预计工作量 ,t3.F0019 as 任务的预计工作量 , to_char(t3.startdate,'yyyy-MM-dd') as 任务的预计开始时间 , to_char(t3.enddate,'yyyy-MM-dd') as 任务的预计结束时间 , to_char(t3.actualstartdate,'yyyy-MM-dd') as 任务的实际开始时间 , to_char(t3.actualenddate,'yyyy-MM-dd') as 任务的实际结束时间 ,t3.worktime as 开发任务的实际工时 ,t3.bugcount 需求bug数 ,t3.bugworktime as 需求修改bug耗时 ,t3.bugworktime/(t3.worktime+t3.bugworktime) as 需求对应BUG的平均工时 -- ,t3.bugsharecount as bug经验分享的数量 from sprt_orgobject t1 left join org_userextendinfo t2 on t1.userid = t2.userid -- 99：任务中止 left join ( select t2.name , t2.requirementid , t3.name as requirementname --任务的开始时间 , t2.startdate -- 任务的结束时间 , t2.enddate , t.ownerid -- 任务的实际开始开发时间 , t2.f0010 as actualstartdate , t2.f0011 as actualenddate , t5.bugcount -- 开发任务的实际工时 , t4.worktime -- 需求修改BUG耗时 , t6.bugworktime -- BUG分享的数量 ,t7.bugsharecount ,t.workload as taskownerWorkload ,t2.F0019 from sirmpm_taskowner t -- type=1是开发任务 left join sirmpm_task t2 on t.taskid = t2.objid and t2.type = 1 left join sirmpm_requirement t3 on t2.requirementid = t3.objid -- 开发任务的实际工时 left join ( select t.taskid , t.ownerid , sum(t.worktime) / 8 as worktime from sirmpm_updatetasklog t where 1 = 1 group by t.taskid,t.ownerid) t4 on t2.objid = t4.taskid and t.ownerid = t4.ownerid -- 这个需求下的BUG数量 left join ( select t.requirementid , count(1) as bugcount from sirmpm_buginfo t left join sirmpm_task t1 on t1.f0016 = t.bugid and t1.f0020 = '0' group by t.requirementid) t5 on t3.objid = t5.requirementid -- BUG的工作时间 left join ( select t.requirementid,sum(t2.worktime) as bugworktime from sirmpm_buginfo t left join sirmpm_task t1 on t1.f0016 = t.bugid and t1.f0020 = '0' left join ( select t.taskid , sum(t.worktime) / 8 as worktime from sirmpm_updatetasklog t group by t.taskid) t2 on t2.taskid = t1.objid group by t.requirementid) t6 on t6.requirementid = t3.objid -- 每个人的BUG经验分享数量 left join (select t2.requirementid,t.inputid,count(1) as bugsharecount from sirmpm_bugexperienceshare t left join sirmpm_buginfo t2 on t.buginfoid=t2.objid where t.flag=1 group by t2.requirementid,t.inputid ) t7 on t7.requirementid=t3.objid and t7.inputid=t.ownerid where t.flag = 1 and to_char(t.enddate,'yyyyMMdd') >= '20180401' and t.status != 99 and t3.checktask = 1 and t3.checktesttask = 1 -- 需求的状态测试通过,现场验证通过，发布现场 and t3.status in (41,45,50) ) t3 on t1.orgid = t3.ownerid where t1.objecttype = 1 and t1.unittype is null and t1.inservice = 1 and t2.where1 = 4 and (t3.name is not null or t3.requirementname is not null ) order by t1.orgname,t3.startdate